## Raw data
Project ID | Region | Client | Project Scope Description | Project Alloction Date | Businessline | Start Date | PAC Date | FAC Date | Project life-days | Key issue
Saretho | Mt. Kenya | Safaricom | Site build | 2023-08-28 | BTS | 2023-09-26 | 2024-02-14 | 2024-03-15 | 403 | FAC Sign off under Circulations
Nakuru KBC | Rift Valley | Safaricom | Site build | 2023-09-01 | BTS | 2023-10-31 | 2024-06-19 | 2024-07-19 | 368 | Delayed PO Issuance
Kahawa_Downs _Acquisition | Nairobi | Safaricom | Acquisition | 2024-02-23 | BTS | 2024-02-23 | 2024-11-19 | 2024-12-19 | 253 | Delayed PO Issuance
Galmart supermarket_Acquisition | Nairobi | Safaricom | Acquisition | 2023-11-28 | BTS | 2024-02-23 | 2024-11-19 | 2024-12-19 | 253 | FAC Sign off under Circulations
East-West Apartments | Nairobi | Safaricom | Indoor | 2024-04-05 | BTS | 2024-04-09 | 2024-11-19 | 2024-12-19 | 207 | Delayed PO Issuance
Airtel Emboasis | Mt. Kenya | Safaricom | TI | 2024-04-12 | BTS | 2024-07-10 | 2024-11-19 | 2024-10-14 | 115 | Delayed PO Issuance and Sign off
Airtel_Colo_Per_Contractor New Sites (Battery, Rectifier and Generator Upgrade)MK,NE | Mt. Kenya | Safaricom | Power upgrade | 2024-05-05 | BTS | 2024-05-05 | 2024-11-19 | 2024-12-19 | 181 | Delayed PO Issuance and Sign off
Airtel_Colo_Per_Contractor New Sites (Battery, Rectifier and Generator Upgrade)NW,WN | Nairobi | Safaricom | Power upgrade | 2024-05-05 | BTS | 2024-05-05 | 2024-11-19 | 2024-12-19 | 181 | Delayed PO Issuance and Sign off
ATC Lunza | Western | Safaricom | Collocation | 2024-06-03 | BTS | 2024-07-08 | 2024-10-17 | 2024-10-17 | 117 | Delayed PO Issuance and Sign off
Optimization-Huawei Expansion - 800 new | Rift Valley | Safaricom | Optimization | 2024-06-04 | BTS | 2024-06-04 | 2024-11-19 | 2024-12-19 | 151 | Delayed PO Issuance and Sign off
Optimization -Huawei Expansion - L1800 | Nairobi East | Safaricom | Optimization | 2024-06-04 | BTS | 2024-06-04 | 2024-11-19 | 2024-12-19 | 151 | Delayed PO Issuance and Sign off
Optimization - Huawei Expansion - UL2100 | Nairobi East | Safaricom | Optimization | 2024-06-04 | BTS | 2024-06-04 | 2024-11-19 | 2024-12-19 | 151 | Delayed PO Issuance and Sign off
Kipsigis highland | Western | Safaricom | Small_cell | 2024-06-06 | BTS | 2024-07-13 | 2024-11-19 | 2024-12-19 | 112 | FAC Sign off under Circulations
Seal Oriwo | Western | Safaricom | TI | 2024-06-13 | BTS | 2024-06-13 | 2024-11-19 | 2024-10-25 | 142 | Delayed PO Issuance and Sign off
Seal Mayanja | Western | Safaricom | TI | 2024-06-13 | BTS | 2024-06-13 | 2024-10-17 | 2024-10-17 | 142 | FAC Sign off under Circulations
Airtel collocation surveys | Western | Safaricom | Surveys | 2024-07-02 | BTS | 2024-07-04 | 2024-10-23 | 2024-10-23 | 121 | Delayed PO Issuance and Sign off
Koyamo Island | Nyanza, Bondo | ATC | DV building | 2023-09-20 | BTS | 2023-10-04 | 2024-09-13 | 2024-10-13 | 395 | Pending FAC SDS/QA Availabity
Wundanyi Rd | Nairobi | Safaricom | survey and restoration | 2024-07-23 | BTS | 2024-08-05 | 2024-11-19 | 2024-12-19 | 89 | Delayed PO Issuance
Blessed House | Nairobi | Safaricom | IBS | 2024-07-31 | BTS | 2024-07-31 | 2024-11-19 | 2024-12-19 | 94 | FAC Sign off under Circulations
Haven House | Nairobi | Safaricom | IBS | 2024-07-31 | BTS | 2024-07-31 | 2024-11-19 | 2024-12-19 | 94 | FAC Sign off under Circulations
Mogondo | Rift Valley | Safaricom | TI | 2024-07-29 | BTS | 2024-07-29 | 2024-11-19 | 2024-12-19 | 96 | Delayed PO Issuance and Sign off
Itibo Resort | Western | Safaricom | TI | 2024-07-29 | BTS | 2024-07-29 | 2024-11-19 | 2024-12-19 | 96 | FAC Sign off under Circulations
Nakuru KBC - Variation scope | Rift Valley | Safaricom | Site build | 2024-04-18 | BTS | 2023-10-31 | 2024-11-19 | 2024-12-19 | 368 | Delayed PO Issuance
Berur/Lengut | Rift Valley | Safaricom | Site build | 2024-10-12 | BTS | 2024-09-07 | 2024-11-19 | 2024-12-19 | 56 | Delayed PO Issuance and Sign off
Kiambuthi | Mt. Kenya | ATC | Site build | 2023-03-31 | BTS | 2023-03-31 | 2023-05-25 | 2024-09-12 | 582 | Delayed PO Issuance and Sign off
Bububu | Likoni | ATC | Site build | 2023-09-24 | BTS | 2023-09-26 | 2024-01-26 | 2024-09-23 | 403 | Delayed PO Issuance and Sign off
Olchorro | Kajiado | ATC | Site build | 2023-10-17 | BTS | 2023-10-21 | 2024-12-12 | 2024-09-19 | 378 | Delayed PO Issuance and Sign off
Kanamai mwatundu | Kilifi | ATC | Site build | 2023-10-18 | BTS | 2023-10-20 | 2024-12-28 | 2024-08-22 | 379 | Delayed PO Issuance and Sign off
Chepkorio | Elgeiyo marakwet | ATC | Site build | 2023-10-31 | BTS | 2023-11-02 | 2024-02-13 | 2024-09-11 | 366 | Delayed PO Issuance and Sign off
Mutunguru | Kiambu | ATC | Site build | 2023-11-20 | BTS | 2023-11-22 | 2024-04-03 | 2024-11-10 | 346 | Delayed PO Issuance and Sign off
Tawa | Machakos | ATC | Site build | 2023-11-22 | BTS | 2023-11-24 | 2024-02-23 | 2024-03-24 | 344 | Delayed PO Issuance and Sign off
Kambura-ini | Mt. Kenya | Safaricom | Acquisition | 2023-03-13 | BTS | 2023-03-13 | 2024-11-19 | 2024-12-19 | 600 | Awaiting RFI/Access/ Third Party Concerns
Kirinyaga Inoi | Mt. Kenya | ATC | Site build | 2023-11-04 | BTS | 2023-11-04 | 2024-08-28 | 2024-10-07 | 364 | Delayed PO Issuance and Sign off
Makka Towers Site acquisition | Nairobi | Safaricom | Acquisition | 2024-08-12 | BTS | 2024-07-02 | 2024-11-19 | 2024-12-19 | 123 | FAC Sign off under Circulations
Mombasa Miritini | Coast | ATC | Solar | 2023-12-05 | BTS | 2024-02-27 | 2024-04-26 | 2024-05-26 | 249 | Delayed PO Issuance and Sign off
Kilifi kiwandani | Coast | ATC | Solar | 2023-12-05 | BTS | 2024-02-27 | 2024-04-22 | 2024-05-22 | 249 | Delayed PO Issuance and Sign off
Additional sectors 3 sites MK | Mt. Kenya | Safaricom | Optimization | 2024-08-24 | BTS | 2024-08-24 | 2024-11-19 | 2024-12-19 | 70 | FAC Sign off under Circulations
Kapletingi | Elgeiyo marakwet | ATC | Site build | 2023-12-10 | BTS | 2023-12-12 | 2024-02-08 | 2024-09-24 | 326 | Delayed PO Issuance and Sign off
E&K apartments | Nairobi | Safaricom | IBS | 2024-07-31 | BTS | 2024-09-16 | 2024-11-19 | 2024-12-19 | 47 | Delayed PO Issuance
KU Nyayo | Nairobi | ATC | Site build | 2023-12-20 | BTS | 2023-12-22 | 2024-05-15 | 2024-10-02 | 316 | Delayed PO Issuance and Sign off
Nord mall | Nairobi | Safaricom | IBS | 2024-07-31 | BTS | 2024-09-17 | 2024-11-19 | 2024-12-19 | 46 | Delayed PO Issuance
Kwa ndunda | Mt. Kenya | ATC | Site build | 2023-12-04 | BTS | 2023-12-06 | 2024-01-24 | 2024-08-05 | 332 | Delayed PO Issuance and Sign off
Pareumarti | Samburu | ATC | Site build | 2024-01-03 | BTS | 2024-01-05 | 2024-05-31 | 2024-06-30 | 302 | FAC Sign off under Circulations
Narok Hospital | Rift Valley | Safaricom | Special projects | 2020-11-30 | BTS | 2020-11-30 | 2024-05-28 | 2024-05-28 | 1433 | Delayed PO Issuance and Sign off
Ushuru sacco | Nairobi | Safaricom | Indoor | 2022-03-21 | BTS | 2022-03-21 | 2024-11-19 | 2024-12-19 | 957 | Pending Materials
ADC_Gotu | Mt. Kenya | Safaricom | TI | 2023-02-21 | BTS | 2023-02-21 | 2024-08-20 | 2024-08-20 | 620 | Delayed PO Issuance and Sign off
ADC_Moite_Hill 775 | Mt. Kenya | Safaricom | TI | 2023-03-18 | BTS | 2024-05-13 | 2024-11-19 | 2024-12-19 | 173 | Awaiting RFI/Access/ Third Party Concerns
ATC_Garabey 595 | Mt. Kenya | Safaricom | TI | 2023-03-18 | BTS | 2024-05-13 | 2024-11-19 | 2024-12-19 | 173 | Awaiting RFI/Access/ Third Party Concerns
ATC_HADI | Mt. Kenya | Safaricom | TI | 2023-03-18 | BTS | 2024-05-13 | 2024-11-19 | 2024-12-19 | 173 | Awaiting RFI/Access/ Third Party Concerns
ADC_Saru | Mt. Kenya | Safaricom | TI | 2023-03-18 | BTS | 2024-05-13 | 2024-11-19 | 2024-12-19 | 173 | Awaiting RFI/Access/ Third Party Concerns
Bahati annexe | Nairobi | ATC | Site build | 2024-02-10 | BTS | 2024-02-12 | 2024-04-03 | 2024-07-08 | 264 | Delayed PO Issuance and Sign off
ADC_Illeret_Junction 850 | Mt. Kenya | Safaricom | TI | 2023-03-18 | BTS | 2024-05-13 | 2024-11-19 | 2024-12-19 | 173 | Awaiting RFI/Access/ Third Party Concerns
Munithu | Makueni | ATC | Site build | 2024-02-13 | BTS | 2024-02-15 | 2024-03-08 | 2024-11-29 | 261 | FAC Sign off under Circulations
ADC_Idhido_Camp_MGF | Mt. Kenya | Safaricom | TI | 2023-03-18 | BTS | 2023-03-18 | 2024-07-17 | 2024-07-17 | 595 | Delayed PO Issuance and Sign off
Thika MSR | Kiambu | Safaricom | Racking | 2023-04-03 | BTS | 2023-08-15 | 2024-11-19 | 2024-06-14 | 445 | Delayed PO Issuance and Sign off
Hela Clothing | Nairobi | Safaricom | Indoor | 2023-07-05 | BTS | 2023-08-02 | 2024-04-18 | 2024-04-18 | 458 | Delayed PO Issuance and Sign off
Bumbe TTC | Western | Safaricom | Decomissioning | 2023-09-06 | BTS | 2024-01-03 | 2024-05-06 | 2024-05-06 | 304 | Delayed PO Issuance and Sign off
Clay creek Apartments | Nairobi | Safaricom | Indoor | 2023-09-15 | BTS | 2024-02-03 | 2024-04-29 | 2024-04-29 | 273 | Delayed PO Issuance and Sign off
Allied Industial | Nairobi | Safaricom | Indoor | 2023-09-15 | BTS | 2024-01-06 | 2024-02-20 | 2024-02-20 | 301 | Delayed PO Issuance and Sign off
Glaxosmithkline_ Acquisition | Nairobi | Safaricom | Indoor | 2024-02-23 | BTS | 2024-02-23 | 2024-05-31 | 2024-05-31 | 253 | Delayed PO Issuance and Sign off
Nyabera Nyatoto | Homa bay | ATC | Site build | 2024-03-12 | BTS | 2024-03-14 | 2024-06-07 | 2024-11-29 | 233 | Pending FAC SDS/QA Availabity
Sunton_Silver_Street - Acquisition | Nairobi | Safaricom | Indoor | 2024-02-23 | BTS | 2024-02-23 | 2024-05-31 | 2024-05-31 | 253 | Delayed PO Issuance and Sign off
Karen Exchange | Nairobi | ATC | DC upgrade | 2024-03-23 | BTS | 2024-03-23 | 2024-11-19 | 2024-09-17 | 224 | Delayed PO Issuance and Sign off
Embu stage | Embu | ATC | Site build | 2024-03-27 | BTS | 2024-03-29 | 2024-07-12 | 2024-09-12 | 218 | Delayed PO Issuance and Sign off
Gathiga stage | Kiambu | ATC | Site build | 2024-03-29 | BTS | 2024-04-09 | 2024-06-10 | 2024-11-29 | 207 | Delayed PO Issuance and Sign off
Masaba Health center | Migori | ATC | Site build | 2024-03-29 | BTS | 2024-04-07 | 2024-06-12 | 2024-11-29 | 209 | Pending FAC SDS/QA Availabity
Vugurugani | Kwale | ATC | Site build | 2024-03-29 | BTS | 2024-04-07 | 2024-08-08 | 2024-11-29 | 209 | Pending FAC SDS/QA Availabity
Kamakis_Paleah_Acquisition | Nairobi | Safaricom | Indoor | 2024-02-23 | BTS | 2024-02-23 | 2024-05-31 | 2024-05-31 | 253 | Delayed PO Issuance and Sign off
Palacina_Acquisition | Nairobi | Safaricom | Indoor | 2024-02-23 | BTS | 2024-02-23 | 2024-05-31 | 2024-05-31 | 253 | Delayed PO Issuance and Sign off
Josma_Plaza_Acquisition | Nairobi | Safaricom | Indoor | 2024-02-23 | BTS | 2024-02-23 | 2024-05-31 | 2024-05-31 | 253 | Delayed PO Issuance and Sign off
Gracious Apartments_Acquisition | Nairobi | Safaricom | Indoor | 2024-02-23 | BTS | 2024-02-23 | 2024-05-31 | 2024-05-31 | 253 | Delayed PO Issuance and Sign off
Avalon Apartments | Nairobi | Safaricom | Indoor | 2023-09-28 | BTS | 2023-12-15 | 2024-03-14 | 2024-03-14 | 323 | Delayed PO Issuance and Sign off
Duruma Sandton hotel | Nairobi | Safaricom | Rooftop | 2023-11-04 | BTS | 2024-01-12 | 2024-09-06 | 2024-09-06 | 295 | Delayed PO Issuance and Sign off
Kitale lukhuna | Rift Valley | Safaricom | TI | 2023-12-05 | BTS | 2023-12-09 | 2024-02-04 | 2024-03-05 | 329 | Delayed PO Issuance and Sign off
Smart Meter Installation | Nairobi North | Safaricom | smart meter installation- Special | 2023-12-08 | BTS | 2023-12-16 | 2024-06-14 | 2024-11-29 | 322 | Awaiting RFI/Access/ Third Party Concerns
Uhuru Park_cow site | Nairobi | Safaricom | TI | 2023-12-11 | BTS | 2023-12-13 | 2024-05-22 | 2024-05-22 | 325 | Delayed PO Issuance and Sign off
Mabruk_Apartments_SmallCell | Nairobi | Safaricom | Rooftop | 2023-12-28 | BTS | 2024-01-21 | 2024-03-12 | 2024-03-12 | 286 | Delayed PO Issuance and Sign off
ATC Cherangani | Rift Valley | Safaricom | TI | 2024-01-12 | BTS | 2024-02-06 | 2024-03-09 | 2024-04-08 | 270 | Delayed PO Issuance and Sign off
DWDM_Lessos KPLC 7 sites | Rift Valley | Safaricom | DWDM | 2024-01-15 | BTS | 2024-03-14 | 2024-05-20 | 2024-05-20 | 233 | Delayed PO Issuance and Sign off
Kambura_ini | Mt. Kenya | Safaricom | Site build | 2024-01-15 | BTS | 2024-02-10 | 2024-06-13 | 2024-07-17 | 266 | Delayed PO Issuance and Sign off
Ambwere Plaza | Western | Safaricom | Decomissioning | 2024-01-23 | BTS | 2024-02-21 | 2024-05-15 | 2024-05-15 | 255 | Delayed PO Issuance and Sign off
Mautuma-milimani | Western | Safaricom | TI | 2024-01-24 | BTS | 2024-01-27 | 2024-07-08 | 2024-07-08 | 280 | Delayed PO Issuance and Sign off
ADC-Paka | Rift Valley | Safaricom | TI | 2024-02-05 | BTS | 2024-02-28 | 2024-05-30 | 2024-05-30 | 248 | Delayed PO Issuance and Sign off
ADC_Mukutani | Rift Valley | Safaricom | TI | 2024-02-05 | BTS | 2024-02-29 | 2024-05-30 | 2024-05-30 | 247 | Delayed PO Issuance and Sign off
Palacina_Hotel | Nairobi | Safaricom | Rooftop | 2024-02-12 | BTS | 2024-04-03 | 2024-08-23 | 2024-08-23 | 213 | Delayed PO Issuance and Sign off
Lwesero | Western | Safaricom | TI | 2024-02-16 | BTS | 2024-02-20 | 2024-04-26 | 2024-04-26 | 256 | Delayed PO Issuance and Sign off
Nyabururu | Western | Safaricom | TI | 2024-02-16 | BTS | 2024-02-21 | 2024-08-20 | 2024-08-20 | 255 | Delayed PO Issuance and Sign off
Ruiru-kamakis | Nairobi | Safaricom | Indoor | 2024-02-23 | BTS | 2024-06-12 | 2024-11-19 | 2024-09-18 | 143 | Delayed PO Issuance and Sign off
Banda_School_add sector | Nairobi | Safaricom | Indoor | 2024-02-27 | BTS | 2024-02-28 | 2024-05-23 | 2024-05-23 | 248 | Delayed PO Issuance and Sign off
Isiolo/Bullo china state construction | Mt. Kenya | Safaricom | TI | 2024-03-02 | BTS | 2024-06-04 | 2024-08-20 | 2024-08-20 | 151 | Delayed PO Issuance and Sign off
Garbatulla Height adjustment | Mt. Kenya | Safaricom | TI | 2024-03-02 | BTS | 2024-05-28 | 2024-06-22 | 2024-06-22 | 158 | Delayed PO Issuance and Sign off
L.Naivasha Resort | Rift Valley | Safaricom | Small_cell | 2024-03-08 | BTS | 2024-03-14 | 2024-05-23 | 2024-05-23 | 233 | Delayed PO Issuance and Sign off
Kapkiam | Kericho | ATC | Site build | 2024-05-01 | BTS | 2024-05-04 | 2024-07-11 | 2024-11-29 | 182 | Snag Clearance
Mayenje secondary | Busia | ATC | Site build | 2024-05-01 | BTS | 2024-05-04 | 2024-07-25 | 2024-11-29 | 182 | Pending FAC SDS/QA Availabity
Muhanda Primary | Vihiga | ATC | Site build | 2024-05-01 | BTS | 2024-05-04 | 2024-09-11 | 2024-10-11 | 182 | Snag Clearance
ATC-Tendo_Estate | Nairobi East | ATC | Collocation | 2024-05-03 | BTS | 2024-05-08 | 2024-06-13 | 2024-06-13 | 178 | Delayed PO Issuance and Sign off
ATC-Mihango | Nairobi East | ATC | Collocation | 2024-05-03 | BTS | 2024-05-08 | 2024-06-13 | 2024-06-13 | 178 | Delayed PO Issuance and Sign off
Kahawa_sukari | Nairobi | Safaricom | Indoor | 2024-03-21 | BTS | 2024-03-23 | 2024-05-29 | 2024-05-29 | 224 | Delayed PO Issuance and Sign off
Battery installations 8 RV sites | Rift Valley | Safaricom | DC upgrade | 2024-03-28 | BTS | 2024-06-07 | 2024-09-24 | 2024-09-24 | 148 | Delayed PO Issuance and Sign off
Olomunyani_MGF_OUTD_RMT | Rift Valley | Safaricom | Collocation | 2024-04-03 | BTS | 2024-05-16 | 2024-07-12 | 2024-07-12 | 170 | Delayed PO Issuance and Sign off
Kerugoya_Mukinduri_OUTA_MGF | Mt. Kenya | Safaricom | Collocation | 2024-04-03 | BTS | 2024-05-11 | 2024-06-13 | 2024-06-13 | 175 | Delayed PO Issuance and Sign off
AbdiWako_Primary_School | Mt. Kenya | Safaricom | Collocation | 2024-04-03 | BTS | 2024-04-03 | 2024-11-19 | 2024-12-19 | 213 | Awaiting RFI/Access/ Third Party Concerns
Telkom_Afweini | Mt. Kenya | Safaricom | Collocation | 2024-04-03 | BTS | 2024-04-03 | 2024-11-19 | 2024-12-19 | 213 | Awaiting RFI/Access/ Third Party Concerns
Saretho_OUTA_HUB | Mt. Kenya | Safaricom | Collocation | 2024-04-03 | BTS | 2024-04-03 | 2024-11-19 | 2024-12-19 | 213 | Awaiting RFI/Access/ Third Party Concerns
Ilkerin_OUTD_MGF_RMT | Rift Valley | Safaricom | Collocation | 2024-04-03 | BTS | 2024-04-03 | 2024-08-09 | 2024-08-09 | 213 | Delayed PO Issuance and Sign off
Eresteno_Primary_School | Mt. Kenya | Safaricom | Collocation | 2024-04-03 | BTS | 2024-04-03 | 2024-11-19 | 2024-12-19 | 213 | Awaiting RFI/Access/ Third Party Concerns
Duce_OUTA_HUB_MGF_VKS_RMT | Mt. Kenya | Safaricom | Collocation | 2024-04-03 | BTS | 2024-04-03 | 2024-08-05 | 2024-08-05 | 213 | Delayed PO Issuance and Sign off
MW link 10 hops &Link Recoveries - Imaroro_Town_Center, Kitui kzanzau,telkom aitong,Ewasu re-location | Mt. Kenya | Safaricom | Optimization | 2024-04-03 | BTS | 2024-06-23 | 2024-09-13 | 2024-09-13 | 132 | Delayed PO Issuance and Sign off
Sangailu_S_OUTA_MGF_VKS_RMT | Mt. Kenya | Safaricom | Collocation | 2024-04-09 | BTS | 2024-06-06 | 2024-06-19 | 2024-06-19 | 149 | Delayed PO Issuance and Sign off
Munyu_Naromoru | Mt. Kenya | ATC | Site build | 2024-05-28 | BTS | 2024-05-29 | 2024-08-23 | 2024-11-29 | 157 | Pending FAC SDS/QA Availabity
Chepkoit Embobut | Rift Valley | ATC | Site build | 2024-05-28 | BTS | 2024-05-29 | 2024-08-08 | 2024-11-29 | 157 | Pending FAC SDS/QA Availabity
Maraigushu | Coast | ATC | Site build | 2024-05-28 | BTS | 2024-05-29 | 2024-08-23 | 2024-11-29 | 157 | Pending FAC SDS/QA Availabity
SARIF_OUTA_VKS_MGF_RMT | Mt. Kenya | Safaricom | Collocation | 2024-04-09 | BTS | 2024-05-30 | 2024-06-19 | 2024-06-19 | 156 | Delayed PO Issuance and Sign off
Dukana_OUTA_S_MGF_VKS_RMT | Mt. Kenya | Safaricom | Collocation | 2024-04-09 | BTS | 2024-04-09 | 2024-11-19 | 2024-12-19 | 207 | Awaiting RFI/Access/ Third Party Concerns
SAKI_OUTA_MGF_RMT | Mt. Kenya | Safaricom | Collocation | 2024-04-09 | BTS | 2024-06-29 | 2024-08-05 | 2024-08-05 | 126 | Delayed PO Issuance and Sign off
RTI_South_MGF | Nairobi East | Safaricom | Collocation | 2024-04-16 | BTS | 2024-05-17 | 2024-06-13 | 2024-06-13 | 169 | Delayed PO Issuance and Sign off
Arabia_OUTA_S_MGF_VKS_RMT | Mt. Kenya | Safaricom | Collocation | 2024-04-16 | BTS | 2024-04-16 | 2024-11-19 | 2024-12-19 | 200 | Awaiting RFI/Access/ Third Party Concerns
MALKARUKA_OUTA_MGF_RMT | Mt. Kenya | Safaricom | Collocation | 2024-04-16 | BTS | 2024-07-13 | 2024-09-06 | 2024-09-06 | 112 | Delayed PO Issuance and Sign off
Oltepesi_OUTE_MGF | Nairobi East | Safaricom | Collocation | 2024-04-22 | BTS | 2024-05-17 | 2024-06-13 | 2024-06-13 | 169 | Delayed PO Issuance and Sign off
Lodungokwe_OUTA_RMT | Mt. Kenya | Safaricom | Collocation | 2024-04-22 | BTS | 2024-06-16 | 2024-07-08 | 2024-07-08 | 139 | Delayed PO Issuance and Sign off
Matho_Primary_School | Mt. Kenya | Safaricom | Collocation | 2024-04-22 | BTS | 2024-04-22 | 2024-11-19 | 2024-12-19 | 194 | Awaiting RFI/Access/ Third Party Concerns
Kwa_Ndumbi | Mt. Kenya | ATC | Site build | 2024-06-10 | BTS | 2024-06-11 | 2024-11-19 | 2024-12-19 | 144 | PAC Sign off under Circulations
ATL_Dale suites | Mt. Kenya | Safaricom | TI | 2024-04-25 | BTS | 2024-05-16 | 2024-08-20 | 2024-08-20 | 170 | Delayed PO Issuance and Sign off
KBC Nakuru | Rift Valley | Safaricom | Optimization | 2024-04-28 | BTS | 2024-04-28 | 2024-11-19 | 2024-12-19 | 188 | Pending Materials
Kericho shivling | Rift Valley | ATC | Collocation | 2024-06-13 | BTS | 2024-06-22 | 2024-11-19 | 2024-12-19 | 133 | Pending PAC QA/SDS Availabity
Churo hill | Mt. Kenya | ATC | Site build | 2024-06-15 | BTS | 2024-06-17 | 2024-09-23 | 2024-10-23 | 138 | Snag Clearance
Dandora Police | Nairobi | ATC | Site build | 2024-06-15 | BTS | 2024-06-16 | 2024-08-08 | 2024-11-29 | 139 | FAC Sign off under Circulations
Kirima meru | Nairobi | ATC | Site build | 2024-07-02 | BTS | 2024-07-04 | 2024-11-19 | 2024-12-19 | 121 | Pending PAC QA/SDS Availabity
Arembe Ndhiwa | Nairobi | ATC | Site build | 2024-07-02 | BTS | 2024-07-04 | 2024-10-25 | 2024-11-24 | 121 | Snag Clearance
Ossen primary | Nairobi | ATC | Site build | 2024-07-02 | BTS | 2024-07-04 | 2024-09-11 | 2024-10-11 | 121 | Pending FAC SDS/QA Availabity
REREC - Kitui Cluster -21 sites | kitui | REREC | Solar | 2024-06-28 | BTS | 2024-07-04 | 2024-11-19 | 2024-12-19 | 121 | Delayed PO Issuance and Sign off
REREC - Wajir Cluster- 12 sites | Wajir | REREC | Solar | 2024-06-28 | BTS | 2024-07-04 | 2024-11-19 | 2024-12-19 | 121 | Awaiting RFI/Access/ Third Party Concerns
Movenpick Hotel | Nairobi | Safaricom | TI | 2024-05-01 | BTS | 2024-05-10 | 2024-06-21 | 2024-06-21 | 176 | Delayed PO Issuance and Sign off
Mai Mahiu | Rift Valley | Safaricom | TI | 2024-05-12 | BTS | 2024-05-21 | 2024-08-20 | 2024-08-20 | 165 | Delayed PO Issuance and Sign off
Kitale sec 6 | Rift Valley | Safaricom | TI | 2024-05-15 | BTS | 2024-05-23 | 2024-07-18 | 2024-07-18 | 163 | Delayed PO Issuance and Sign off
Saraishie Primary | Nairobi | ATC | Site build | 2024-07-09 | BTS | 2024-07-11 | 2024-11-19 | 2024-12-19 | 114 | Delayed PO Issuance and Sign off
Karen - Consolidation Sites | Nairobi | ATC | Consolidation and Relocation | 2024-07-10 | BTS | 2024-09-19 | 2024-11-19 | 2024-12-19 | 44 | Delayed PO Issuance and Sign off
Maragoli_Forest | Kakamega | ATC | Consolidation and Relocation | 2024-07-10 | BTS | 2024-07-10 | 2024-11-19 | 2024-12-19 | 115 | Delayed PO Issuance and Sign off
KISUMU_ MAMBOLEO | Kisumu | ATC | Consolidation and Relocation | 2024-07-10 | BTS | 2024-09-19 | 2024-11-19 | 2024-12-19 | 44 | Delayed PO Issuance and Sign off
New Muthaiga Mall | Nairobi | ATC | Consolidation and Relocation | 2024-07-10 | BTS | 2024-07-10 | 2024-11-19 | 2024-12-19 | 115 | Delayed PO Issuance and Sign off
Muranga Town- Consolidation Sites | Muranga | ATC | Consolidation and Relocation | 2024-07-10 | BTS | 2024-09-19 | 2024-11-19 | 2024-12-19 | 44 | Delayed PO Issuance and Sign off
ADC_Kileleshwa Police station | Nairobi | Safaricom | TI | 2024-05-15 | BTS | 2024-05-24 | 2024-07-31 | 2024-07-31 | 162 | Delayed PO Issuance and Sign off
Muranga Technical | Muranga | ATC | Site build | 2024-08-10 | BTS | 2024-08-12 | 2024-11-19 | 2024-12-19 | 82 | Pending Materials
Tangulbei | Tangulbei | ATC | Site build | 2024-07-30 | BTS | 2024-07-30 | 2024-11-19 | 2024-12-19 | 95 | Delayed PO Issuance and Sign off
Ongata rongai | Nairobi | ATC | Site build | 2024-07-31 | BTS | 2024-07-31 | 2024-09-24 | 2024-10-24 | 94 | Snag Clearance
Kahawa_Barracks | Nairobi | Safaricom | Collocation | 2023-06-26 | BTS | 2023-06-26 | 2024-05-30 | 2024-05-30 | 495 | Delayed PO Issuance and Sign off
Indoor Rectifier swap- 8 sites WN | Rift Valley | Safaricom | Rectifier swap | 2024-04-02 | BTS | 2024-04-02 | 2024-09-16 | 2024-10-16 | 214 | Delayed PO Issuance and Sign off
Indoor to Outdoor conversion 10 sites | Western | Safaricom | Indoor to Outdoor | 2024-05-09 | BTS | 2024-07-08 | 2024-11-19 | 2024-12-19 | 117 | FAC Sign off under Circulations
Ngurumani | Nairobi | Safaricom | Collocation | 2024-06-03 | BTS | 2024-07-05 | 2024-07-12 | 2024-07-12 | 120 | Delayed PO Issuance and Sign off
Kisii_Nyamware | Western | Safaricom | Collocation | 2024-06-03 | BTS | 2024-07-08 | 2024-07-24 | 2024-07-24 | 117 | Delayed PO Issuance and Sign off
Nkondi | Mt. Kenya | Safaricom | Collocation | 2024-06-03 | BTS | 2024-06-28 | 2024-07-15 | 2024-07-24 | 127 | Delayed PO Issuance and Sign off
Lord Erolle | Nairobi West | Safaricom | site Restoration | 2024-06-04 | BTS | 2024-06-06 | 2024-11-19 | 2024-10-04 | 149 | Delayed PO Issuance and Sign off
Rooftop site Audits | Western, Nairobi | Safaricom | Surveys | 2024-07-02 | BTS | 2024-07-04 | 2024-08-14 | 2024-09-13 | 121 | Delayed PO Issuance and Sign off
Seal Kibigori | Western | Safaricom | TI | 2024-07-08 | BTS | 2024-07-28 | 2024-11-19 | 2024-12-19 | 97 | Delayed PO Issuance and Sign off
Kaptich | Rift Valley | Safaricom | TI | 2024-07-29 | BTS | 2024-07-29 | 2024-11-19 | 2024-12-19 | 96 | Awaiting RFI/Access/ Third Party Concerns
Kesses_Kilombero | Rift Valley | Safaricom | TI | 2024-07-29 | BTS | 2024-07-29 | 2024-11-19 | 2024-12-19 | 96 | Awaiting RFI/Access/ Third Party Concerns
Marigat_Town_A | Rift Valley | Safaricom | TI | 2024-07-29 | BTS | 2024-07-29 | 2024-11-19 | 2024-12-19 | 96 | Awaiting RFI/Access/ Third Party Concerns
Mogotio_Kinoyo | Rift Valley | Safaricom | TI | 2024-07-29 | BTS | 2024-07-29 | 2024-11-19 | 2024-12-19 | 96 | Awaiting RFI/Access/ Third Party Concerns
Msau | Coast | Safaricom | TI | 2024-07-29 | BTS | 2024-07-29 | 2024-11-19 | 2024-12-19 | 96 | Awaiting RFI/Access/ Third Party Concerns
Kipsigis Highlands, Kisii mwembe | Rift Valley | Safaricom | Acquisition | 2024-07-31 | BTS | 2024-07-31 | 2024-08-30 | 2024-08-30 | 94 | Delayed PO Issuance and Sign off
Josma Plaza | Nairobi | Safaricom | Acquisition | 2024-05-07 | BTS | 2024-05-07 | 2024-08-30 | 2024-08-30 | 179 | Delayed PO Issuance and Sign off
AYDEN TOWERS | Nairobi | Safaricom | Acquisition | 2023-02-16 | BTS | 2023-02-16 | 2024-11-19 | 2024-12-19 | 625 | Scope not done/to Be closed
Lake Naivasha Resort | Nairobi | Safaricom | Design | 2024-07-24 | BTS | 2024-07-24 | 2024-08-30 | 2024-08-30 | 101 | Delayed PO Issuance and Sign off
Sunton Silver Street | Nairobi | Safaricom | Design | 2024-07-18 | BTS | 2024-07-18 | 2024-08-30 | 2024-08-30 | 107 | Delayed PO Issuance and Sign off
Josma Plaza | Nairobi | Safaricom | Design | 2024-07-15 | BTS | 2024-07-15 | 2024-08-30 | 2024-08-30 | 110 | Delayed PO Issuance and Sign off
Glaxo Smithkline | Nairobi | Safaricom | Design | 2024-07-15 | BTS | 2024-07-15 | 2024-08-30 | 2024-08-30 | 110 | Delayed PO Issuance and Sign off
Edenville Ph 1 | Nairobi | Safaricom | Design | 2024-07-15 | BTS | 2024-07-15 | 2024-08-30 | 2024-08-30 | 110 | Delayed PO Issuance and Sign off
Craft Silicon | Nairobi | Safaricom | Design | 2024-07-15 | BTS | 2024-07-15 | 2024-08-30 | 2024-08-30 | 110 | Delayed PO Issuance and Sign off
Sunton First Street | Nairobi | Safaricom | Design | 2024-06-12 | BTS | 2024-06-12 | 2024-08-30 | 2024-08-30 | 143 | Delayed PO Issuance and Sign off
Sunton_Third_Street - Ebenezer Apartments | Nairobi | Safaricom | Design | 2024-05-16 | BTS | 2024-05-16 | 2024-08-30 | 2024-08-30 | 170 | Delayed PO Issuance and Sign off
Kisumu Kudho | Western | Safaricom | TI | 2023-09-15 | BTS | 2023-09-15 | 2024-11-19 | 2024-12-19 | 414 | Scope not done/to Be closed
Nyali Maweni Site acquisition | Coast | Safaricom | Acquisition | 2024-06-15 | BTS | 2024-06-15 | 2024-08-30 | 2024-08-30 | 140 | Delayed PO Issuance and Sign off
Bahrain Towers Site acquisition | Nairobi | Safaricom | Acquisition | 2024-08-12 | BTS | 2024-08-12 | 2024-08-30 | 2024-08-30 | 82 | Delayed PO Issuance and Sign off
DWDM_Nairobi_Nakuru KPLC 10 sites | Rift Valley | Safaricom | Acquisition | 2024-08-02 | BTS | 2024-08-02 | 2024-11-19 | 2024-12-19 | 92 | Delayed PO Issuance and Sign off
Tilisi | Nairobi | Safaricom | Acquisition | 2024-06-15 | BTS | 2024-07-02 | 2024-11-19 | 2024-12-19 | 123 | FAC Sign off under Circulations
Kakamega-sahajanad | Western | Safaricom | Acquisition | 2024-06-15 | BTS | 2024-07-02 | 2024-11-19 | 2024-12-19 | 123 | Awaiting RFI/Access/ Third Party Concerns
Blessed House | Nairobi | Safaricom | Acquisition | 2024-07-31 | BTS | 2024-07-31 | 2024-11-19 | 2024-09-17 | 94 | Delayed PO Issuance and Sign off
Kahawa Wendani | Nairobi | ATC | Solar | 2024-07-31 | BTS | 2024-08-02 | 2024-11-19 | 2024-10-14 | 92 | Delayed PO Issuance and Sign off
Kimana Lerai | Kajiado | ATC | Site build | 2024-07-09 | BTS | 2024-07-11 | 2024-11-19 | 2024-12-19 | 114 | Pending Materials
Haven House | Nairobi | Safaricom | Acquisition | 2024-07-31 | BTS | 2024-07-31 | 2024-11-19 | 2024-09-23 | 94 | Delayed PO Issuance and Sign off
E&K, St Joseph Kahawa sukari- Acqusition | Rift Valley | Safaricom | Acquisition | 2024-07-31 | BTS | 2024-07-31 | 2024-09-17 | 2024-10-17 | 94 | Delayed PO Issuance and Sign off
19941_NW_NM1556 Edenville | Nairobi | Safaricom | Acquisition | 2024-07-31 | BTS | 2024-07-31 | 2024-11-19 | 2024-12-19 | 94 | Awaiting RFI/Access/ Third Party Concerns
Kambi Ya Elijah | Rift Valley | ATC | Site build | 2024-09-17 | BTS | 2024-09-23 | 2024-11-19 | 2024-12-19 | 40 | Delayed PO Issuance and Sign off
MW link 4 hops &Link Recoveries | Rift Valley | Safaricom | Optimization | 2024-10-12 | BTS | 2024-10-12 | 2024-11-19 | 2024-12-19 | 21 | Delayed PO Issuance and Sign off
North Muthaiga | Nairobi West | Safaricom | Collocation | 2024-10-08 | BTS | 2024-10-08 | 2024-11-19 | 2024-12-19 | 25 | Delayed PO Issuance and Sign off
Lessesia | Coast | ATC | Site build | 2024-10-08 | BTS | 2024-10-11 | 2024-11-19 | 2024-12-19 | 22 | Delayed PO Issuance and Sign off
Kambi Ya Elijah | Rift Valley | Safaricom | TI | 2024-09-17 | BTS | 2024-10-23 | 2024-11-19 | 2024-12-19 | 10 | Delayed PO Issuance and Sign off
Osorongai Hill-Kapsabet Singarwa | Rift Valley | Safaricom | SDC | 2023-02-03 | Fiber | 2023-10-23 | 2024-03-25 | 2024-11-29 | 376 | Delayed CRF Approval
Osorongai Hill-Kapsabet Singarwa-CRF | Rift Valley | Safaricom | SDC | 2023-02-03 | Fiber | 2023-10-23 | 2024-03-25 | 2024-11-29 | 376 | Delayed CRF Approval
EAST_WEST_APARTMENTS | Nairobi | Safaricom | FTTS-2G/IBS | 2024-02-05 | Fiber | 2024-03-26 | 2024-04-18 | 2024-11-29 | 221 | FAC Sign off under Circulations
Tena_Royal_Court | Nairobi | Safaricom | FTTS-2G/IBS | 2024-02-01 | Fiber | 2024-08-16 | 2024-11-11 | 2024-11-29 | 78 | FAC Awaiting SFE & MSP FE Availability
Kayole_Mwangaza_ERRU | Nairobi | Safaricom | FTTS-2G/IBS | 2024-02-01 | Fiber | 2024-10-02 | 2024-11-11 | 2024-11-29 | 31 | Pending Access /Third Party Concerns
KAG_Karagita_Church_Mihango | Nairobi | Safaricom | FTTS-2G/IBS | 2024-07-11 | Fiber | 2024-07-26 | 2024-09-05 | 2024-11-29 | 99 | FAC Sign off under Circulations
MWEA CARE DESK ZESORT SAFARICOM SHOP | Nairobi | Safaricom | FTTS-2G/IBS | 2024-07-23 | Fiber | 2024-08-06 | 2024-09-25 | 2024-11-29 | 88 | FAC Sign off under Circulations
Ongata_Rongai_Napacha | Nairobi | Safaricom | FTTS-2G/IBS | 2024-08-08 | Fiber | 2024-08-23 | 2024-10-08 | 2024-11-29 | 71 | FAC Sign off under Circulations
DELTA_CHAMBERS_IBS | Nairobi | Safaricom | FTTS-2G/IBS | 2024-08-05 | Fiber | 2024-08-19 | 2024-10-09 | 2024-11-29 | 75 | FAC Sign off under Circulations
Rungiri | Nairobi | Safaricom | FTTS-2G/IBS | 2024-08-29 | Fiber | 2024-09-21 | 2024-11-03 | 2024-11-29 | 42 | FAC Awaiting SFE & MSP FE Availability
E&K_Apartments_Kahawa_wendani | Nairobi | Safaricom | FTTS-2G/IBS | 2024-09-04 | Fiber | 2024-09-16 | 2024-11-12 | 2024-11-29 | 47 | FAC Sign off under Circulations
THE_NORD_MALL_RUIRU_ERRU | Nairobi | Safaricom | FTTS-2G/IBS | 2024-09-04 | Fiber | 2024-09-16 | 2024-11-12 | 2024-11-29 | 47 | FAC Sign off under Circulations
Connection Services(21/10/24-20/11/24) | Nairobi | Safaricom | FTTH Connections | 2024-05-22 | Fiber | 2024-09-21 | 2024-07-21 | 2024-11-29 | 42 | Ongoing
Relocation Services (21/10/24-20/11/24) | Nairobi | Safaricom | FTTH Relocations | 2024-05-22 | Fiber | 2024-09-21 | 2024-07-21 | 2024-11-29 | 42 | Ongoing
Drop Poles-21/4/23-26/7/24 | Nairobi/Embu | Safaricom | FTTH Connections | 2022-08-24 | Fiber | 2023-04-21 | 2024-11-29 | 2024-11-29 | 561 | FAC Sign off under Circulations
Jetview FDT 1 Dens | Nairobi | Safaricom | FTTH Rollout | 2023-09-19 | Fiber | 2023-12-15 | 2024-06-22 | 2024-11-29 | 323 | Delayed As-built Design
Jetview FDT 2 Dens | Nairobi | Safaricom | FTTH Rollout | 2023-09-19 | Fiber | 2023-12-15 | 2023-05-31 | 2024-11-29 | 323 | Completed-Delayed PO Issuance
Ex Kays FDT 1-Silver Pearl | Juja | Safaricom | FTTH Rollout | 2023-02-20 | Fiber | 2023-05-26 | 2023-05-26 | 2024-11-29 | 526 | Delayed As-built Design
SYOKIMAU ASPURA FDT 1-Impl | Nairobi | Safaricom | FTTH Rollout | 2023-09-19 | Fiber | 2023-12-15 | 2023-12-15 | 2024-11-29 | 323 | Delayed As-built Design
Mlolongo FDT 1 Impl | Nairobi | Safaricom | FTTH Rollout | 2023-09-19 | Fiber | 2023-12-15 | 2023-12-15 | 2024-11-29 | 323 | Delayed As-built Design
TWIGA COURT KATANI FDT 1 Impl | Nairobi | Safaricom | FTTH Rollout | 2023-09-19 | Fiber | 2024-03-22 | 2024-03-22 | 2024-11-29 | 225 | Delayed As-built Design
Fairfield Estate FDT 1 Impl | Nairobi | Safaricom | FTTH Rollout | 2023-09-19 | Fiber | 2024-03-22 | 2024-03-22 | 2024-11-29 | 225 | Delayed As-built Design
TPA Court FDT 1 Impl | Nairobi | Safaricom | FTTH Rollout | 2023-09-19 | Fiber | 2024-04-03 | 2024-06-28 | 2024-11-29 | 213 | Delayed As-built Design
Grayland FDT Ph 6 Impl | Nairobi | Safaricom | FTTH Rollout | 2023-09-19 | Fiber | 2024-04-04 | 2024-06-28 | 2024-11-29 | 212 | Delayed As-built Design
Legacy Apartment Impl | Nairobi | Safaricom | FTTH Rollout | 2023-09-19 | Fiber | 2024-05-16 | 2024-06-28 | 2024-11-29 | 170 | Delayed As-built Design
Mombasa Island Mwembe FDT 4 Impl | Coast | Safaricom | FTTH Rollout | 2023-12-01 | Fiber | 2024-08-31 | 2024-06-08 | 2024-11-29 | 63 | Warranty Period
Mombasa Island Mwembe FDT 5 Impl | Coast | Safaricom | FTTH Rollout | 2023-12-01 | Fiber | 2024-07-11 | 2024-09-18 | 2024-11-29 | 114 | Warranty Period
Mombasa Island Tudor FDT 5 Impl | Coast | Safaricom | FTTH Rollout | 2023-12-01 | Fiber | 2024-06-27 | 2024-09-18 | 2024-11-29 | 128 | Warranty Period
Mombasa Island Winners Chapel FDT 1 Impl | Coast | Safaricom | FTTH Rollout | 2023-11-08 | Fiber | 2024-06-29 | 2024-09-12 | 2024-11-29 | 126 | Warranty Period
Mombasa Island Winners Chapel FDT 2 Impl | Coast | Safaricom | FTTH Rollout | 2023-11-08 | Fiber | 2024-07-05 | 2024-04-22 | 2024-11-29 | 120 | Warranty Period
MOMBASA ISLAND GANJONI FDT 1 Impl | Coast | Safaricom | FTTH Rollout | 2023-11-08 | Fiber | 2024-05-25 | 2024-09-18 | 2024-11-29 | 161 | Warranty Period
MOMBASA ISLAND GANJONI FDT 2 Impl | Coast | Safaricom | FTTH Rollout | 2023-11-08 | Fiber | 2024-05-25 | 2024-09-12 | 2024-11-29 | 161 | Warranty Period
MOMBASA ISLAND GANJONI FDT 3 Impl | Coast | Safaricom | FTTH Rollout | 2023-11-08 | Fiber | 2024-05-25 | 2024-09-18 | 2024-11-29 | 161 | Warranty Period
Mombasa Island Old Town FDT 1 Impl | Coast | Safaricom | FTTH Rollout | 2023-12-07 | Fiber | 2024-07-14 | 2024-10-25 | 2024-11-29 | 111 | Warranty Period
Mombasa Island Mwembe FDT 3 Impl | Coast | Safaricom | FTTH Rollout | 2023-12-07 | Fiber | 2024-07-19 | 2024-08-19 | 2024-11-29 | 106 | Warranty Period
Mombasa Island Ex Tudor FDT 9 Dens Impl | Coast | Safaricom | FTTH Rollout | 2023-12-07 | Fiber | 2024-07-11 | 2024-09-18 | 2024-11-29 | 114 | Warranty Period
MOMBASA ISLAND TUDOR FDT 6 Impl | Coast | Safaricom | FTTH Rollout | 2023-11-08 | Fiber | 2024-06-27 | 2024-08-12 | 2024-11-29 | 128 | Delayed As-built Design
MOMBASA ISLAND TUDOR FDT 4 Impl | Coast | Safaricom | FTTH Rollout | 2023-11-08 | Fiber | 2024-06-27 | 2024-09-18 | 2024-11-29 | 128 | Warranty Period
SYOKIMAU FAIRFIED PARK IMPL | Syokimau | Safaricom | FTTH Rollout | 2024-01-25 | Fiber | 2024-05-31 | 2024-06-28 | 2024-11-29 | 155 | Delayed As-built Design
UTAWALA DENSIFICATION ADJ ZURI APARTMENTS IMPL | Utawala | Safaricom | FTTH Rollout | 2024-04-25 | Fiber | 2024-05-29 | 2024-06-28 | 2024-11-29 | 157 | Delayed As-built Design
ICD Business Park | Nairobi | Safaricom | FTTB Rollout | 2022-10-08 | Fiber | 2022-10-30 | 2022-12-19 | 2024-11-29 | 734 | FAC Sign off under Circulations
Ngong Junction Plaza | Nairobi | Safaricom | FTTB Rollout | 2022-10-08 | Fiber | 2022-10-30 | 2022-12-19 | 2024-11-29 | 734 | FAC Sign off under Circulations
Josta | Rift Valley | Safaricom | FTTB Rollout | 2022-06-14 | Fiber | 2022-07-06 | 2022-12-19 | 2024-11-29 | 850 | Awaiting receipting
KOBIRO | Rift Valley | Safaricom | FTTB Rollout | 2022-06-14 | Fiber | 2022-07-06 | 2022-12-19 | 2024-11-29 | 850 | Awaiting receipting
PESAPAL | Nairobi | Safaricom | FTTB Rollout | 2022-02-27 | Fiber | 2022-03-21 | 2023-01-04 | 2024-11-29 | 957 | Pending Access /Third Party Concerns
JAVE BUILDING | Nairobi | Safaricom | FTTB Rollout | 2022-02-27 | Fiber | 2022-03-21 | 2022-12-19 | 2024-11-29 | 957 | FAC Sign off under Circulations
RAICIR BUILDING | Nairobi | Safaricom | FTTB Rollout | 2022-03-20 | Fiber | 2022-04-11 | 2022-12-19 | 2024-11-29 | 936 | FAC Sign off under Circulations
SHEM PLAZA | Nairobi | Safaricom | FTTB Rollout | 2022-03-14 | Fiber | 2022-04-05 | 2023-04-27 | 2024-11-29 | 942 | FAC Sign off under Circulations
Diplomat | Rift Valley | Safaricom | FTTB Rollout | 2023-06-17 | Fiber | 2023-07-09 | 2023-01-04 | 2024-11-29 | 482 | Awaiting receipting
NO 36 LANGIRI RD/Top Touch Marketing Ltd | Nairobi | Safaricom | FTTB Rollout | 2023-03-20 | Fiber | 2023-04-04 | 2023-10-12 | 2024-11-29 | 578 | FAC Sign off under Circulations
ELGON COURT | Nairobi | Safaricom | FTTB Rollout | 2022-11-20 | Fiber | 2023-05-09 | 2023-10-12 | 2024-11-29 | 543 | FAC Sign off under Circulations
SAFARI CENTRE NAIVASHA | Rift Valley | Safaricom | FTTB Rollout | 2022-03-30 | Fiber | 2023-05-09 | 2023-10-23 | 2024-11-29 | 543 | Awaiting receipting
Gemco Hotels | Nairobi | Safaricom | FTTB Rollout | 2023-07-24 | Fiber | 2023-08-06 | 2023-10-23 | 2024-05-20 | 454 | Awaiting receipting
Crestpoint Consult Ltd | Nairobi | Safaricom | FTTB Rollout | 2023-08-16 | Fiber | 2023-08-27 | 2023-10-12 | 2024-11-29 | 433 | FAC Sign off under Circulations
SYMPHONY HOTELS NAIVASHA | Rift Valley | Safaricom | FTTB Rollout | 2023-09-18 | Fiber | 2023-10-01 | 2023-10-23 | 2024-11-29 | 398 | Awaiting receipting
Wamuthoni-Mobilink Technologies | Rift Valley | Safaricom | FTTB Rollout | 2023-07-12 | Fiber | 2023-08-29 | 2023-10-23 | 2024-11-29 | 431 | Awaiting receipting
ALMAH PLAZA | Nairobi | Safaricom | FTTB Rollout | 2022-04-12 | Fiber | 2022-06-15 | 2022-06-01 | 2024-11-29 | 871 | Completed-Delayed PO Issuance
Jahazi | Nairobi | Safaricom | FTTB Rollout | 2023-04-29 | Fiber | 2023-07-08 | 2024-10-27 | 2024-11-29 | 483 | FAC Sign off under Circulations
Maximum Business Centre | Nairobi | Safaricom | FTTB Rollout | 2023-10-12 | Fiber | 2023-12-02 | 2024-07-04 | 2024-05-28 | 336 | Awaiting receipting
Matumbo House | Nairobi | Safaricom | FTTB Rollout | 2023-10-24 | Fiber | 2023-12-03 | 2024-01-04 | 2024-11-29 | 335 | Pending Access /Third Party Concerns
Times U Sacco Nkubu | Mt Kenya | Safaricom | FTTB Rollout | 2024-01-18 | Fiber | 2024-02-04 | 2024-07-04 | 2024-05-21 | 272 | Awaiting receipting
Kiricop House - Kerugoya | Mt Kenya | Safaricom | FTTB Rollout | 2024-01-03 | Fiber | 2024-02-16 | 2024-09-30 | 2024-11-29 | 260 | FAC Sign off under Circulations
Winter Villas Resort & Spa Ltd | Mt Kenya | Safaricom | FTTB Rollout | 2024-01-03 | Fiber | 2024-02-08 | 2024-07-04 | 2024-05-28 | 268 | Awaiting receipting
MLANGO BUILDING CHUKA | Mt Kenya | Safaricom | FTTB Rollout | 2024-02-22 | Fiber | 2024-03-25 | 2024-04-18 | 2024-11-29 | 222 | Completed-Delayed PO Issuance
Magunas Membley | Nairobi | Safaricom | FTTB Rollout | 2024-03-23 | Fiber | 2024-04-13 | 2024-05-06 | 2024-11-29 | 203 | FAC Sign off under Circulations
Sentrum Communications Company Ltd | Nairobi | Safaricom | FTTB Rollout | 2022-12-09 | Fiber | 2022-12-17 | 2024-09-27 | 2024-11-29 | 686 | FAC Sign off under Circulations
Daima Sacco | Nairobi | Safaricom | FTTB Rollout | 2023-08-27 | Fiber | 2023-09-07 | 2024-10-15 | 2024-11-29 | 422 | Awaiting receipting
Kiricop House Kerugoya | Mt Kenya | Safaricom | FTTB Rollout | 2024-04-24 | Fiber | 2024-05-27 | 2024-09-27 | 2024-11-29 | 159 | FAC Sign off under Circulations
Exfinity Building Kagio | Mt Kenya | Safaricom | FTTB Rollout | 2024-04-25 | Fiber | 2024-05-19 | 2024-10-27 | 2024-11-29 | 167 | FAC Sign off under Circulations
Kingdom Bank Meru | Mt Kenya | Safaricom | FTTB Rollout | 2024-04-25 | Fiber | 2024-05-11 | 2024-10-27 | 2024-11-29 | 175 | FAC Sign off under Circulations
Huduma Centre Kirinyaga | Mt Kenya | Safaricom | FTTB Rollout | 2024-05-09 | Fiber | 2024-06-05 | 2024-07-24 | 2024-11-29 | 150 | FAC Sign off under Circulations
Kwa Mwalimu | Mt Kenya | Safaricom | FTTB Rollout | 2024-05-09 | Fiber | 2024-05-25 | 2024-09-03 | 2024-11-29 | 161 | FAC Sign off under Circulations
Norwich Union | Nairobi | Safaricom | FTTB Optimization | 2023-09-10 | Fiber | 2023-09-16 | 2023-10-25 | 2024-11-29 | 413 | FAC Sign off under Circulations
Naivas Outering-Deejina | Nairobi | Safaricom | FTTB Optimization | 2024-01-17 | Fiber | 2024-02-03 | 2024-03-06 | 2024-11-29 | 273 | Completed-Delayed PO Issuance
UNGA HOUSE | Nairobi | Safaricom | FTTB Optimization | 2023-10-11 | Fiber | 2024-02-16 | 2024-10-02 | 2024-11-29 | 260 | Completed-Delayed PO Issuance
KU Plaza | Nairobi | Safaricom | FTTB Optimization | 2024-01-30 | Fiber | 2024-04-28 | 2024-04-24 | 2024-11-29 | 188 | FAC Awaiting SFE & MSP FE Availability
FEDHA_TOWERS/ECOBANK_TOWERS | Nairobi | Safaricom | FTTB Optimization | 2024-04-16 | Fiber | 2024-05-27 | 2024-06-19 | 2024-11-29 | 159 | FAC Awaiting SFE & MSP FE Availability
Kassmart Supermakets Mwiki | Nairobi | Safaricom | FTTB Rollout | 2024-05-16 | Fiber | 2024-06-06 | 2024-07-02 | 2024-11-29 | 149 | Completed-Delayed PO Issuance
Grace Apartments Mweiga | Mt Kenya | Safaricom | FTTB Rollout | 2024-05-16 | Fiber | 2024-06-11 | 2024-07-25 | 2024-11-29 | 144 | FAC Sign off under Circulations
MOMBASA ISLAND LIWATONI FDT 1 | Mombasa&Changamwe | Safaricom | FTTH Rollout | 2024-04-16 | Fiber | 2024-08-12 | 2024-10-25 | 2024-11-29 | 82 | Warranty Period
CHANGAMWE MKINDANI FDT 1 Impl | Mombasa&Changamwe | Safaricom | FTTH Rollout | 2024-04-16 | Fiber | 2024-08-13 | 2024-10-25 | 2024-11-29 | 81 | Warranty Period
CHANGAMWE MKINDANI FDT 2 Impl | Mombasa&Changamwe | Safaricom | FTTH Rollout | 2024-04-16 | Fiber | 2024-08-15 | 2024-10-25 | 2024-11-29 | 79 | Warranty Period
CHANGAMWE MKINDANI FDT 3 Impl | Mombasa&Changamwe | Safaricom | FTTH Rollout | 2024-04-16 | Fiber | 2024-08-19 | 2024-10-25 | 2024-11-29 | 75 | Warranty Period
CHANGAMWE MWANGEKA FDT 1 Impl | Mombasa&Changamwe | Safaricom | FTTH Rollout | 2024-04-16 | Fiber | 2024-08-13 | 2024-10-25 | 2024-11-29 | 81 | Warranty Period
CHANGAMWE MWANGEKA FDT 2 Impl | Mombasa&Changamwe | Safaricom | FTTH Rollout | 2024-04-16 | Fiber | 2024-08-14 | 2024-10-25 | 2024-11-29 | 80 | Warranty Period
CHANGAMWE MWANGEKA FDT 3 Impl | Mombasa&Changamwe | Safaricom | FTTH Rollout | 2024-04-16 | Fiber | 2024-08-26 | 2024-10-25 | 2024-11-29 | 68 | Warranty Period
Magunas Sagana | Mt Kenya | Safaricom | FTTB Rollout | 2024-05-31 | Fiber | 2024-06-14 | 2024-07-25 | 2024-11-29 | 141 | FAC Sign off under Circulations
SDC FY 24-25: Bungoma-Kakamega | Greater Western | Safaricom | SDC | 2024-06-08 | Fiber | 2024-09-30 | 2024-09-26 | 2024-11-29 | 33 | Ongoing
Nakuru CBD - CBA Centre-Nairobi Womens Hospital-Nakuru | Rift Valley | Safaricom | FTTB Rollout | 2024-06-09 | Fiber | 2024-06-27 | 2024-09-27 | 2024-11-29 | 128 | Awaiting receipting
Nakuru Hyrax - Crater Medical-Nairobi Womens Hospital-Nakuru | Rift Valley | Safaricom | FTTB Rollout | 2024-06-09 | Fiber | 2024-06-26 | 2024-09-12 | 2024-11-29 | 129 | Awaiting receipting
Tsavo Fedha Impl | Nairobi | Safaricom | FTTH Rollout | 2024-06-17 | Fiber | 2024-09-03 | 2024-09-11 | 2024-11-29 | 60 | OAC Sign off under Circulations
Cheche Studios (Karoki Chebii Ltd) | Rift Valley | Safaricom | FTTB Rollout | 2024-06-27 | Fiber | 2024-07-29 | 2024-09-12 | 2024-11-29 | 96 | Awaiting receipting
Karrot Studios (Dinach Company Ltd) | Rift Valley | Safaricom | FTTB Rollout | 2024-06-27 | Fiber | 2024-07-16 | 2024-09-27 | 2024-11-29 | 109 | Awaiting receipting
NYEWASCO – Kangemi Nyeri Plant | Mt Kenya | Safaricom | FTTB Rollout | 2024-06-27 | Fiber | 2024-07-12 | 2024-08-16 | 2024-11-29 | 113 | FAC Sign off under Circulations
NYEWASCO – Kamakwa Plant | Mt Kenya | Safaricom | FTTB Rollout | 2024-06-27 | Fiber | 2024-07-11 | 2024-10-02 | 2024-11-29 | 114 | FAC Sign off under Circulations
EQUITY BANK-GILGIL | Rift Valley | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-31 | 2024-09-12 | 2024-11-29 | 94 | Awaiting receipting
MWALIMU PLAZA (POST BANK KABARNET) | Rift Valley | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-30 | 2024-09-12 | 2024-11-29 | 95 | Awaiting receipting
MAZIWA HOUSE 1990(POST BANK MOLO) | Rift Valley | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-28 | 2024-09-12 | 2024-11-29 | 97 | Awaiting receipting
FAULU BANK MOLO BRANCH | Rift Valley | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-27 | 2024-09-12 | 2024-11-29 | 98 | Awaiting receipting
FAULU BANK NAROK BRANCH | Rift Valley | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-27 | 2024-09-12 | 2024-11-29 | 98 | Awaiting receipting
FAULU BANK KABARNET BRANCH | Rift Valley | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-29 | 2024-09-12 | 2024-11-29 | 96 | Awaiting receipting
CONSOLIDATED BANK -MURANG'A PRIMARY | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-19 | 2024-09-27 | 2024-11-29 | 106 | FAC Sign off under Circulations
SIDIAN BANK LIMITED-KERUGOYA | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-25 | 2024-09-27 | 2024-11-29 | 100 | FAC Sign off under Circulations
EQUITY BANK-KERUGOYA | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-25 | 2024-09-27 | 2024-11-29 | 100 | FAC Sign off under Circulations
FAMILY BANK LIMITED-KERUGOYA | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-19 | 2024-08-22 | 2024-11-29 | 106 | FAC Sign off under Circulations
FAMILY BANK LIMITED-MURANGA | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-19 | 2024-09-27 | 2024-11-29 | 106 | FAC Sign off under Circulations
FAMILY BANK LIMITED-NYERI | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-24 | 2024-09-27 | 2024-11-29 | 101 | FAC Sign off under Circulations
POSTBANK NYERI | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-26 | 2024-09-27 | 2024-11-29 | 99 | FAC Sign off under Circulations
POSTBANK KERUGOYA | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-06 | Fiber | 2024-07-24 | 2024-09-27 | 2024-11-29 | 101 | FAC Sign off under Circulations
Kigumo Technical and Vocational College | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-11 | Fiber | 2024-08-03 | 2024-09-27 | 2024-11-29 | 91 | FAC Sign off under Circulations
Juniper Green Farm | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-11 | Fiber | 2024-08-08 | 2024-09-27 | 2024-11-29 | 86 | FAC Sign off under Circulations
Chloride Exide Nyeri | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-18 | Fiber | 2024-08-10 | 2024-09-27 | 2024-11-29 | 84 | Completed-Delayed PO Issuance
Chloride Exide Meru | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-18 | Fiber | 2024-08-05 | 2024-09-27 | 2024-11-29 | 89 | FAC Sign off under Circulations
Kambi Msituni Resort | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-17 | Fiber | 2024-07-11 | 2024-09-27 | 2024-11-29 | 114 | FAC Sign off under Circulations
Central Bank of Kenya (CBK) Meru | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-16 | Fiber | 2024-08-03 | 2024-09-27 | 2024-11-29 | 91 | FAC Sign off under Circulations
Imenti Complex | Mt Kenya | Safaricom | FTTB Rollout | 2024-07-16 | Fiber | 2024-08-03 | 2024-09-27 | 2024-11-29 | 91 | FAC Sign off under Circulations
Office of the Auditor General (OAG) Embu | Mt Kenya | Safaricom | FTTB Rollout | 2024-08-08 | Fiber | 2024-08-23 | 2024-09-27 | 2024-11-29 | 71 | FAC Sign off under Circulations
KWA MURANGO (THARAKA WOMEN WELFARE PROGRAM) | Mt Kenya | Safaricom | FTTB Rollout | 2024-08-08 | Fiber | 2024-08-28 | 2024-09-27 | 2024-11-29 | 66 | FAC Sign off under Circulations
Rubate Youth Empowerment (PRESBYTERIAN TEACHERS COLLEGE) | Mt Kenya | Safaricom | FTTB Rollout | 2024-08-08 | Fiber | 2024-08-27 | 2024-09-27 | 2024-11-29 | 67 | FAC Sign off under Circulations
Wakanoro Building | Mt Kenya | Safaricom | FTTB Rollout | 2024-08-08 | Fiber | 2024-08-26 | 2024-09-27 | 2024-11-29 | 68 | FAC Sign off under Circulations
Magunas Chuka | Mt Kenya | Safaricom | FTTB Rollout | 2024-08-20 | Fiber | 2024-08-25 | 2024-09-30 | 2024-11-29 | 69 | FAC Sign off under Circulations
Magunas Thika Chap Chap | Mt Kenya | Safaricom | FTTB Rollout | 2024-08-20 | Fiber | 2024-08-31 | 2024-09-27 | 2024-11-29 | 63 | FAC Sign off under Circulations
St. Mary’s School Nairobi | Nairobi | Safaricom | FTTB Rollout | 2024-09-02 | Fiber | 2024-09-13 | 2026-10-20 | 2024-11-29 | 50 | FAC Awaiting SFE & MSP FE Availability
Tropical Mac EPZ | Mt Kenya | Safaricom | FTTB Rollout | 2024-09-02 | Fiber | 2024-09-16 | 2024-10-15 | 2024-11-29 | 47 | Awaiting receipting
Mwietheri Sacco Society Ltd | Mt Kenya | Safaricom | FTTB Rollout | 2024-09-02 | Fiber | 2024-09-16 | 2024-10-20 | 2024-11-29 | 47 | Awaiting receipting
Emmanuel Supermarket | Mt Kenya | Safaricom | FTTB Rollout | 2024-09-03 | Fiber | 2024-09-18 | 2024-10-20 | 2024-11-29 | 45 | Awaiting receipting
UPPER VIEW HOSTELS (DEMKA DAIRY) | Mt Kenya | Safaricom | FTTB Rollout | 2024-09-03 | Fiber | 2024-09-18 | 2024-10-20 | 2024-11-29 | 45 | Awaiting receipting
IHURURU COUNTY OFFICE/ IHURURU PRIMARY | Mt Kenya | Safaricom | FTTB Rollout | 2024-09-13 | Fiber | 2024-09-27 | 2025-12-04 | 2024-11-29 | 36 | Awaiting receipting
MAGUNA-ANDU WHOLESALERS MANGUYO BRANCH | Mt Kenya | Safaricom | FTTB Rollout | 2024-09-13 | Fiber | 2024-07-25 | 2024-08-26 | 2024-11-29 | 100 | Awaiting receipting
D.O. E CARITAS COMFORT ZONE | Mt Kenya | Safaricom | FTTB Rollout | 2024-09-18 | Fiber | 2024-09-28 | 2024-11-02 | 2024-11-29 | 35 | Awaiting receipting
MERU TEACHERS COLLEGE | Mt Kenya | Safaricom | FTTB Rollout | 2024-09-23 | Fiber | 2024-09-29 | 2024-11-02 | 2024-11-29 | 34 | Awaiting receipting
Grand Venus Hotel | Mt Kenya | Safaricom | FTTB Rollout | 2024-09-19 | Fiber | 2024-10-03 | 2024-11-04 | 2024-11-29 | 30 | Awaiting receipting
Tha Nickolee Hotel | Mt Kenya | Safaricom | FTTB Rollout | 2024-09-19 | Fiber | 2024-10-04 | 2024-11-10 | 2024-11-29 | 29 | Awaiting receipting
14071_NW_LEC30290-Witeithie (Greenfield )_Sector 1_ BOQ ( Highway View Plaza-26hh ,Anns Apartments-26hh ) | JUJA | Safaricom | PTMP | 2024-08-22 | Fiber | 2024-10-11 | 2024-12-10 | 2024-11-29 | 22 | Ongoing
14071_NW_LEC30290-Witeithie (Greenfield )_Sector 1-100HPs | JUJA | Safaricom | PTMP | 2024-08-22 | Fiber | 2024-10-11 | 2024-12-10 | 2024-11-29 | 22 | Ongoing
Muriru Hardware | Mt Kenya | Safaricom | FTTB Rollout | 2024-10-04 | Fiber | 2024-10-16 | 2026-12-15 | 2024-11-29 | 17 | FAC Awaiting SFE & MSP FE Availability
PS Alex Wachira Residence | Mt Kenya | Safaricom | FTTB Rollout | 2024-10-04 | Fiber | 2024-10-17 | 2024-12-21 | 2024-11-29 | 16 | FAC Awaiting SFE & MSP FE Availability
Formulas:
Project life-days = TODAY()-[Start Date]