## Raw data
Project ID | Region | Client | Project Scope Description | Project Alloction Date | Customer Contracted Project Start Date (PO or Allocation Date) | Start Date | PAC Date | FAC Date | Project life-days | Factor
Prj.1 | Rift valley | Kenblast | Construction | 2020-11-30 | 2020-11-30 | 2020-11-30 | 2024-03-25 | 2024-05-28 | 1275 | Quality Concerns
Prj.2 | Nairobi | Kenblast | Optimisation | 2022-03-21 | 2022-03-21 | 2022-03-21 | 2024-09-11 | 2024-09-25 | 919 | Materials Issuance
Prj.3 | Mount Kenya | Kenblast | Optimisation | 2023-02-21 | 2023-02-21 | 2023-02-21 | 2024-09-25 | 2024-08-20 | 546 | Quality Concerns
Prj.4 | Mount Kenya | Kenblast | Optimisation | 2023-03-18 | 2024-05-13 | 2023-03-18 | 2024-09-11 | 2024-09-25 | 557 | Accessibility
Prj.5 | Mount Kenya | Kenblast | Optimisation | 2023-03-18 | 2024-05-13 | 2023-03-18 | 2024-09-11 | 2024-09-25 | 557 | Accessibility
Prj.6 | Mount Kenya | Kenblast | Optimisation | 2023-03-18 | 2024-05-13 | 2023-03-18 | 2024-09-11 | 2024-09-25 | 557 | Accessibility
Prj.7 | Mount Kenya | Kenblast | Optimisation | 2023-03-18 | 2024-05-13 | 2023-03-18 | 2024-09-11 | 2024-09-25 | 557 | Accessibility
Prj.8 | Mount Kenya | Kenblast | Optimisation | 2023-03-18 | 2024-05-13 | 2023-03-18 | 2024-09-11 | 2024-09-25 | 557 | Accessibility
Prj.9 | Mount Kenya | Kenblast | Optimisation | 2023-03-18 | 2023-03-18 | 2023-03-18 | 2024-09-25 | 2024-07-17 | 487 | Quality Concerns
Prj.10 | Kiambu | Kenblast | Optimisation | 2023-04-03 | 2022-02-28 | 2023-08-15 | 2024-09-25 | 2024-06-14 | 304 | Quality Concerns
Prj.11 | Nairobi | Kenblast | Optimisation | 2023-07-05 | 2023-12-05 | 2023-08-02 | 2024-04-18 | 2024-04-18 | 260 | Quality Concerns
Prj.12 | Mount Kenya | Kenblast | Construction | 2023-08-28 | 2023-08-28 | 2023-09-26 | 2024-01-31 | 2024-09-25 | 365 | Materials Issuance
Prj.13 | Rift valley | Kenblast | Construction | 2023-09-01 | 2023-10-17 | 2023-10-31 | 2024-09-11 | 2024-09-25 | 330 | Scope Variations
Prj.14 | Western | Kenblast | Optimisation | 2023-09-06 | 2024-04-18 | 2024-01-03 | 2024-09-25 | 2024-05-06 | 124 | Quality Concerns
Prj.15 | Nairobi | Kenblast | Optimisation | 2023-09-15 | 2023-09-15 | 2024-02-03 | 2024-09-25 | 2024-04-29 | 86 | Quality Concerns
Prj.16 | Nairobi | Kenblast | Optimisation | 2023-09-15 | 2023-09-15 | 2024-01-06 | 2024-09-25 | 2024-02-20 | 45 | Quality Concerns
Prj.17 | Ksumu | Starlenk | Optimisation | 2023-09-20 | 2023-09-20 | 2023-10-04 | 2024-09-11 | 2024-09-25 | 357 | Quality Concerns
Prj.18 | Nairobi | Kenblast | Optimisation | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-09-25 | 2024-05-31 | 98 | Quality Concerns
Prj.19 | Nairobi | Kenblast | Optimisation | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-09-25 | 2024-05-31 | 98 | Quality Concerns
Prj.20 | Nairobi | Kenblast | Optimisation | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-09-25 | 2024-05-31 | 98 | Quality Concerns
Prj.21 | Nairobi | Kenblast | Optimisation | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-09-25 | 2024-05-31 | 98 | Quality Concerns
Prj.22 | Nairobi | Kenblast | Optimisation | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-09-25 | 2024-05-31 | 98 | Quality Concerns
Prj.23 | Nairobi | Kenblast | Optimisation | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-09-25 | 2024-05-31 | 98 | Quality Concerns
Prj.24 | Nairobi | Kenblast | Survey | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-09-11 | 2024-09-25 | 215 | Scope Variations
Prj.25 | Mount kenya | Starlenk | Construction | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2024-09-25 | 2024-09-12 | 531 | Quality Concerns
Prj.26 | Likoni | Starlenk | Construction | 2023-09-24 | 2023-09-24 | 2023-09-26 | 2024-09-11 | 2024-09-25 | 365 | Documentation
Prj.27 | Nairobi | Kenblast | Optimisation | 2023-09-28 | 2023-12-12 | 2023-12-15 | 2024-09-25 | 2024-03-14 | 90 | Quality Concerns
Prj.28 | Kajiado | Starlenk | Construction | 2023-10-17 | 2023-10-17 | 2023-10-21 | 2024-09-25 | 2024-09-19 | 334 | Quality Concerns
Prj.29 | Kilifi | Starlenk | Construction | 2023-10-18 | 2023-10-18 | 2023-10-20 | 2024-09-25 | 2024-08-22 | 307 | Quality Concerns
Prj.30 | Elgeiyo marakwet | Starlenk | Construction | 2023-10-31 | 2023-10-31 | 2023-11-02 | 2024-09-25 | 2024-09-11 | 314 | Quality Concerns
Prj.31 | Nairobi | Kenblast | Construction | 2023-11-04 | 2023-12-06 | 2024-01-12 | 2024-09-25 | 2024-09-06 | 238 | Quality Concerns
Prj.32 | Kiambu | Starlenk | Construction | 2023-11-20 | 2023-11-20 | 2023-11-22 | 2024-09-11 | 2024-09-25 | 308 | Documentation
Prj.33 | Machakos | Starlenk | Construction | 2023-11-22 | 2023-11-22 | 2023-11-24 | 2024-09-11 | 2024-09-25 | 306 | Quality Concerns
Prj.34 | Nairobi | Kenblast | Survey | 2023-11-28 | 2024-02-22 | 2024-02-23 | 2024-09-11 | 2024-09-25 | 215 | Accessibility
Prj.35 | Mount kenya | Starlenk | Construction | 2023-11-04 | 2023-11-04 | 2023-11-04 | 2024-09-11 | 2024-09-25 | 326 | Quality Concerns
Prj.36 | Rift valley | Kenblast | Optimisation | 2023-12-05 | 2024-01-15 | 2023-12-09 | 2024-09-11 | 2024-09-25 | 291 | Quality Concerns
Prj.37 | Coast | Starlenk | Powering System | 2023-12-05 | 2023-12-05 | 2024-02-27 | 2024-09-11 | 2024-09-25 | 211 | Quality Concerns
Prj.38 | Coast | Starlenk | Powering System | 2023-12-05 | 2023-12-06 | 2024-02-27 | 2024-09-11 | 2024-09-25 | 211 | Quality Concerns
Prj.39 | Nairobi North | Kenblast | Powering System | 2023-12-08 | 2023-12-08 | 2023-12-16 | 2024-09-11 | 2024-09-25 | 284 | Accessibility
Prj.40 | Elgeiyo marakwet | Starlenk | Construction | 2023-12-10 | 2023-12-10 | 2023-12-12 | 2024-01-25 | 2024-09-25 | 288 | Quality Concerns
Prj.41 | Nairobi | Kenblast | Optimisation | 2023-12-11 | 2023-12-10 | 2023-12-13 | 2024-05-22 | 2024-05-22 | 161 | Quality Concerns
Prj.42 | Nairobi | Starlenk | Construction | 2023-12-20 | 2023-12-20 | 2023-12-22 | 2024-05-01 | 2024-09-25 | 278 | Documentation
Prj.43 | Nairobi | Kenblast | Construction | 2023-12-28 | 2024-01-15 | 2024-01-21 | 2024-03-12 | 2024-03-12 | 51 | Quality Concerns
Prj.44 | Mount kenya | Starlenk | Construction | 2023-12-04 | 2023-12-06 | 2023-12-06 | 2024-09-25 | 2024-08-05 | 243 | Quality Concerns
Prj.45 | Samburu | Starlenk | Construction | 2024-01-03 | 2024-01-03 | 2024-01-05 | 2024-09-11 | 2024-09-25 | 264 | Client Manegment
Prj.46 | Rift valley | Kenblast | Optimisation | 2024-01-12 | 2024-01-12 | 2024-02-06 | 2024-09-11 | 2024-09-25 | 232 | Quality Concerns
Prj.47 | Rift valley | Kenblast | Optimisation | 2024-01-15 | 2024-02-26 | 2024-03-14 | 2024-05-20 | 2024-05-20 | 67 | Quality Concerns
Prj.48 | Mount Kenya | Kenblast | Construction | 2024-01-15 | 2024-01-15 | 2024-02-10 | 2024-06-11 | 2024-07-17 | 158 | Quality Concerns
Prj.49 | Western | Kenblast | Optimisation | 2024-01-23 | 2024-01-23 | 2024-02-21 | 2024-05-15 | 2024-05-15 | 84 | Quality Concerns
Prj.50 | Western | Kenblast | Optimisation | 2024-01-24 | 2024-01-28 | 2024-01-27 | 2024-09-25 | 2024-07-08 | 163 | Quality Concerns
Prj.51 | Rift valley | Kenblast | Optimisation | 2024-02-05 | 2024-02-05 | 2024-02-28 | 2024-09-25 | 2024-05-30 | 92 | Quality Concerns
Prj.52 | Rift valley | Kenblast | Optimisation | 2024-02-05 | 2024-02-05 | 2024-02-29 | 2024-09-25 | 2024-05-30 | 91 | Quality Concerns
Prj.53 | Nairobi | Starlenk | Construction | 2024-02-10 | 2024-02-10 | 2024-02-12 | 2024-09-25 | 2024-07-08 | 147 | Quality Concerns
Prj.54 | Nairobi | Kenblast | Construction | 2024-02-12 | 2024-02-16 | 2024-04-03 | 2024-09-25 | 2024-08-23 | 142 | Quality Concerns
Prj.55 | Makueni | Starlenk | Construction | 2024-02-13 | 2024-02-13 | 2024-02-15 | 2024-09-11 | 2024-09-25 | 223 | Quality Concerns
Prj.56 | Western | Kenblast | Optimisation | 2024-02-16 | 2024-02-16 | 2024-02-20 | 2024-09-25 | 2024-04-26 | 66 | Quality Concerns
Prj.57 | Western | Kenblast | Optimisation | 2024-02-16 | 2024-02-16 | 2024-02-21 | 2024-09-25 | 2024-08-20 | 181 | Quality Concerns
Prj.58 | Nairobi | Kenblast | Optimisation | 2024-02-23 | 2024-02-23 | 2024-06-12 | 2024-09-25 | 2024-09-18 | 98 | Quality Concerns
Prj.59 | Nairobi | Kenblast | Optimisation | 2024-02-27 | 2024-02-27 | 2024-02-28 | 2024-09-25 | 2024-05-23 | 85 | Quality Concerns
Prj.60 | mount kenya | Kenblast | Optimisation | 2024-03-02 | 2024-03-02 | 2024-06-04 | 2024-09-25 | 2024-08-20 | 77 | Quality Concerns
Prj.61 | Mount Kenya | Kenblast | Optimisation | 2024-03-02 | 2024-03-02 | 2024-05-28 | 2024-09-25 | 2024-06-22 | 25 | Quality Concerns
Prj.62 | Rift valley | Kenblast | Optimisation | 2024-03-08 | 2024-03-08 | 2024-03-14 | 2024-09-25 | 2024-05-23 | 70 | Quality Concerns
Prj.63 | Homa bay | Starlenk | Construction | 2024-03-12 | 2024-03-12 | 2024-03-14 | 2024-09-11 | 2024-09-25 | 195 | Client Manegment
Prj.64 | Nairobi | Kenblast | Optimisation | 2024-03-21 | 2024-03-21 | 2024-03-23 | 2024-09-25 | 2024-05-29 | 67 | Quality Concerns
Prj.65 | Nairobi | Starlenk | Powering System | 2024-03-23 | 2024-03-23 | 2024-03-23 | 2024-09-25 | 2024-09-17 | 178 | Quality Concerns
Prj.66 | Embu | Starlenk | Construction | 2024-03-27 | 2024-03-27 | 2024-03-29 | 2024-09-25 | 2024-09-12 | 167 | Quality Concerns
Prj.67 | Kiambu | Starlenk | Construction | 2024-03-29 | 2024-04-07 | 2024-04-09 | 2024-09-11 | 2024-09-25 | 169 | Client Manegment
Prj.68 | Migori | Starlenk | Construction | 2024-03-29 | 2024-04-05 | 2024-04-07 | 2024-09-11 | 2024-09-25 | 171 | Client Manegment
Prj.69 | Kwale | Starlenk | Construction | 2024-03-29 | 2024-04-05 | 2024-04-07 | 2024-09-11 | 2024-09-25 | 171 | Client Manegment
Prj.70 | Rift valley | Kenblast | Powering System | 2024-03-28 | 2024-06-06 | 2024-06-07 | 2024-09-25 | 2024-09-16 | 101 | Quality Concerns
Prj.71 | Rift valley | Kenblast | Optimisation | 2024-04-03 | 2024-05-16 | 2024-05-16 | 2024-09-25 | 2024-07-12 | 57 | Quality Concerns
Prj.72 | Mount Kenya | Kenblast | Optimisation | 2024-04-03 | 2024-05-11 | 2024-05-11 | 2024-09-25 | 2024-06-13 | 33 | Quality Concerns
Prj.73 | Mount Kenya | Kenblast | Optimisation | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-09-11 | 2024-09-25 | 175 | Accessibility
Prj.74 | Mount Kenya | Kenblast | Optimisation | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-09-11 | 2024-09-25 | 175 | Accessibility
Prj.75 | Mount Kenya | Kenblast | Optimisation | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-09-11 | 2024-09-25 | 175 | Accessibility
Prj.76 | Rift valley | Kenblast | Optimisation | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-09-25 | 2024-08-09 | 128 | Quality Concerns
Prj.77 | Mount Kenya | Kenblast | Optimisation | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-09-11 | 2024-09-25 | 175 | Accessibility
Prj.78 | Mount Kenya | Kenblast | Optimisation | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-09-25 | 2024-08-05 | 124 | Quality Concerns
Prj.79 | Nairobi | Kenblast | Powering System | 2024-04-03 | 2024-06-22 | 2024-06-23 | 2024-09-25 | 2024-09-13 | 82 | Quality Concerns
Prj.80 | Nairobi | Kenblast | Optimisation | 2024-04-05 | 2024-04-05 | 2024-04-09 | 2024-09-11 | 2024-09-25 | 169 | Accessibility
Prj.81 | Mount Kenya | Kenblast | Optimisation | 2024-04-09 | 2024-04-09 | 2024-06-06 | 2024-09-25 | 2024-06-19 | 13 | Quality Concerns
Prj.82 | Mount Kenya | Kenblast | Optimisation | 2024-04-09 | 2024-04-09 | 2024-05-30 | 2024-09-25 | 2024-06-19 | 20 | Quality Concerns
Prj.83 | Mount Kenya | Kenblast | Optimisation | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2024-09-11 | 2024-09-25 | 169 | Accessibility
Prj.84 | Mount Kenya | Kenblast | Optimisation | 2024-04-09 | 2024-04-09 | 2024-06-29 | 2024-09-25 | 2024-08-05 | 37 | Quality Concerns
Prj.85 | Mount Kenya | Kenblast | Optimisation | 2024-04-12 | 2024-04-12 | 2024-07-10 | 2024-09-11 | 2024-09-25 | 77 | Scope Variations
Prj.86 | Nairobi East | Kenblast | Optimisation | 2024-04-16 | 2024-05-14 | 2024-05-17 | 2024-09-25 | 2024-06-13 | 27 | Quality Concerns
Prj.87 | Mount Kenya | Kenblast | Optimisation | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-09-11 | 2024-09-25 | 162 | Accessibility
Prj.88 | Mount Kenya | Kenblast | Optimisation | 2024-04-16 | 2024-04-16 | 2024-07-13 | 2024-09-25 | 2024-09-06 | 55 | Quality Concerns
Prj.89 | Nairobi East | Kenblast | Optimisation | 2024-04-22 | 2024-05-16 | 2024-05-17 | 2024-09-25 | 2024-06-13 | 27 | Quality Concerns
Prj.90 | Mount Kenya | Kenblast | Optimisation | 2024-04-22 | 2024-04-22 | 2024-06-16 | 2024-09-25 | 2024-07-08 | 22 | Quality Concerns
Prj.91 | Mount Kenya | Kenblast | Optimisation | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-09-11 | 2024-09-25 | 156 | Accessibility
Prj.92 | Mount Kenya | Kenblast | Optimisation | 2024-04-25 | 2024-04-25 | 2024-05-16 | 2024-09-25 | 2024-08-20 | 96 | Quality Concerns
Prj.93 | Rift valley | Kenblast | Powering System | 2024-04-28 | 2024-04-28 | 2024-04-28 | 2024-09-11 | 2024-09-25 | 150 | Materials Issuance
Prj.94 | Nairobi | Kenblast | Optimisation | 2024-05-01 | 2024-05-03 | 2024-05-10 | 2024-09-25 | 2024-06-21 | 42 | Quality Concerns
Prj.95 | Kericho | Starlenk | Construction | 2024-05-01 | 2024-04-28 | 2024-05-04 | 2024-09-11 | 2024-09-25 | 144 | Quality Concerns
Prj.96 | Busia | Starlenk | Construction | 2024-05-01 | 2024-04-28 | 2024-05-04 | 2024-09-11 | 2024-09-25 | 144 | Client Manegment
Prj.97 | Vihiga | Starlenk | Construction | 2024-05-01 | 2024-04-28 | 2024-05-04 | 2024-09-11 | 2024-09-25 | 144 | Quality Concerns
Prj.98 | Nairobi East | Starlenk | Optimisation | 2024-05-03 | 2024-05-02 | 2024-05-08 | 2024-06-04 | 2024-06-13 | 36 | Quality Concerns
Prj.99 | Nairobi East | Starlenk | Optimisation | 2024-05-03 | 2024-05-03 | 2024-05-08 | 2024-06-04 | 2024-06-13 | 36 | Quality Concerns
Prj.100 | Rift valley | Kenblast | Optimisation | 2024-05-12 | 2024-05-12 | 2024-05-21 | 2024-09-25 | 2024-08-20 | 91 | Quality Concerns
Prj.101 | Rift valley | Kenblast | Optimisation | 2024-05-15 | 2024-05-15 | 2024-05-23 | 2024-09-25 | 2024-07-18 | 56 | Quality Concerns
Prj.102 | Nairobi | Kenblast | Optimisation | 2024-05-15 | 2024-05-15 | 2024-05-24 | 2024-09-25 | 2024-07-31 | 68 | Quality Concerns
Prj.103 | Rift valley | Kenblast | Powering System | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-09-11 | 2024-09-25 | 215 | Scope Variations
Prj.104 | Rift valley | Kenblast | Powering System | 2023-09-03 | 2023-09-03 | 2023-09-03 | 2024-09-11 | 2024-09-25 | 388 | Scope Variations
Prj.105 | Mt. Kenya | Kenblast | Powering System | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-09-11 | 2024-09-25 | 223 | Scope Variations
Prj.106 | Nairobi | Kenblast | Optimisation | 2023-06-26 | 2023-06-26 | 2023-06-26 | 2024-09-25 | 2024-05-30 | 339 | Quality Concerns
Prj.107 | Western | Kenblast | Optimisation | 2024-04-02 | 2024-04-02 | 2024-04-02 | 2024-09-11 | 2024-09-25 | 176 | Materials Issuance
Prj.108 | Rift valley | Kenblast | Powering System | 2020-10-27 | 2020-10-27 | 2020-10-27 | 2024-09-11 | 2024-09-25 | 1429 | Scope Variations
Prj.109 | Western | Kenblast | Optimisation | 2024-05-09 | 2024-05-09 | 2024-07-08 | 2024-09-11 | 2024-09-25 | 79 | Documentation
Prj.110 | Mt. Kenya | Kenblast | Powering System | 2024-05-05 | 2024-05-05 | 2024-05-05 | 2024-09-11 | 2024-09-25 | 143 | Materials Issuance
Prj.111 | Nairobi | Kenblast | Powering System | 2024-05-05 | 2024-05-05 | 2024-05-05 | 2024-09-11 | 2024-09-25 | 143 | Materials Issuance
Prj.112 | Mount kenya | Starlenk | Construction | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-09-11 | 2024-09-25 | 119 | Client Manegment
Prj.113 | Rift valley | Starlenk | Construction | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-09-11 | 2024-09-25 | 119 | Quality Concerns
Prj.114 | Coast | Starlenk | Construction | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-09-11 | 2024-09-25 | 119 | Quality Concerns
Prj.115 | Nairobi | Kenblast | Optimisation | 2024-06-03 | 2024-06-03 | 2024-07-05 | 2024-09-25 | 2024-07-12 | 7 | Quality Concerns
Prj.116 | Western | Kenblast | Optimisation | 2024-06-03 | 2024-06-03 | 2024-07-08 | 2024-09-11 | 2024-09-25 | 79 | Quality Concerns
Prj.117 | Mount Kenya | Kenblast | Optimisation | 2024-06-03 | 2024-06-03 | 2024-06-28 | 2024-09-11 | 2024-09-25 | 89 | Quality Concerns
Prj.118 | Western | Kenblast | Optimisation | 2024-06-03 | 2024-06-03 | 2024-07-08 | 2024-09-11 | 2024-09-25 | 79 | Accessibility
Prj.119 | Rift valley | Kenblast | Powering System | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-09-11 | 2024-09-25 | 113 | Materials Issuance
Prj.120 | Nairobi East | Kenblast | Powering System | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-09-11 | 2024-09-25 | 113 | Materials Issuance
Prj.121 | Nairobi East | Kenblast | Powering System | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-09-11 | 2024-09-25 | 113 | Materials Issuance
Prj.122 | Nairobi West | Kenblast | Construction | 2024-06-04 | 2024-06-04 | 2024-06-06 | 2024-09-11 | 2024-09-25 | 111 | Scope Variations
Prj.123 | Western | Kenblast | Optimisation | 2024-06-06 | 2024-07-06 | 2024-07-13 | 2024-09-11 | 2024-09-25 | 74 | Scope Variations
Prj.124 | Mount Kenya | Starlenk | Construction | 2024-06-10 | 2024-06-10 | 2024-06-11 | 2024-09-11 | 2024-09-25 | 106 | Client Manegment
Prj.125 | Western | Kenblast | Optimisation | 2024-06-13 | 2024-06-13 | 2024-06-13 | 2024-09-11 | 2024-09-25 | 104 | Accessibility
Prj.126 | Western | Kenblast | Optimisation | 2024-06-13 | 2024-06-13 | 2024-06-13 | 2024-09-11 | 2024-09-25 | 104 | Accessibility
Prj.127 | Rift valley | Starlenk | Optimisation | 2024-06-13 | 2024-06-13 | 2024-06-22 | 2024-09-11 | 2024-09-25 | 95 | Client Manegment
Prj.128 | Mount Kenya | Starlenk | Construction | 2024-06-15 | 2024-06-15 | 2024-06-17 | 2024-09-11 | 2024-09-25 | 100 | Scope Variations
Prj.129 | Nairobi | Starlenk | Construction | 2024-06-15 | 2024-06-15 | 2024-06-16 | 2024-09-11 | 2024-09-25 | 101 | Client Manegment
Prj.130 | Nairobi | Starlenk | Construction | 2024-07-02 | 2024-07-02 | 2024-07-04 | 2024-09-11 | 2024-09-25 | 83 | Client Manegment
Prj.131 | Nairobi | Starlenk | Construction | 2024-07-02 | 2024-07-02 | 2024-07-04 | 2024-09-11 | 2024-09-25 | 83 | Client Manegment
Prj.132 | Nairobi | Starlenk | Construction | 2024-07-02 | 2024-07-02 | 2024-07-04 | 2024-09-11 | 2024-09-25 | 83 | Quality Concerns
Prj.133 | kitui | Kenblast | Powering System | 2024-06-28 | 2024-07-02 | 2024-07-04 | 2024-09-11 | 2024-09-25 | 83 | Accessibility
Prj.134 | Wajir | Kenblast | Powering System | 2024-06-28 | 2024-07-02 | 2024-07-04 | 2024-09-11 | 2024-09-25 | 83 | Accessibility
Prj.135 | Nairobi | Kenblast | Survey | 2024-07-02 | 2024-07-02 | 2024-07-04 | 2024-09-11 | 2024-09-25 | 83 | Quality Concerns
Prj.136 | Western | Kenblast | Survey | 2024-07-02 | 2024-07-02 | 2024-07-04 | 2024-09-11 | 2024-09-25 | 83 | Materials Issuance
Prj.137 | Western | Kenblast | Optimisation | 2024-07-08 | 2024-07-08 | 2024-07-28 | 2024-09-11 | 2024-09-25 | 59 | Scope Variations
Prj.138 | Nairobi | Starlenk | Construction | 2024-07-09 | 2024-07-09 | 2024-07-11 | 2024-09-11 | 2024-09-25 | 76 | Materials Issuance
Prj.139 | Nairobi | Starlenk | Powering System | 2024-07-10 | 2024-07-10 | 2024-07-29 | 2024-09-11 | 2024-09-25 | 58 | Materials Issuance
Prj.140 | Kisumu | Starlenk | Powering System | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2024-09-11 | 2024-09-25 | 77 | Materials Issuance
Prj.141 | Kisumu | Starlenk | Powering System | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2024-09-11 | 2024-09-25 | 77 | Materials Issuance
Prj.142 | Kiambu | Starlenk | Powering System | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2024-09-11 | 2024-09-25 | 77 | Materials Issuance
Prj.143 | Muranga | Starlenk | Powering System | 2024-07-10 | 2024-07-10 | 2024-07-29 | 2024-09-11 | 2024-09-25 | 58 | Materials Issuance
Prj.144 | Nairobi | Kenblast | Survey | 2024-07-23 | 2024-07-23 | 2024-08-05 | 2024-09-11 | 2024-09-25 | 51 | Scope Variations
Prj.145 | Muranga | Starlenk | Construction | 2024-08-10 | 2024-07-30 | 2024-08-12 | 2024-09-11 | 2024-09-25 | 44 | Materials Issuance
Prj.146 | Tangulbei | Starlenk | Construction | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-09-11 | 2024-09-25 | 57 | Client Manegment
Prj.147 | Nairobi | Starlenk | Construction | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-09-11 | 2024-09-25 | 56 | Client Manegment
Prj.148 | Nairobi | Kenblast | Optimisation | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-09-11 | 2024-09-25 | 56 | Scope Variations
Prj.149 | Nairobi | Kenblast | Optimisation | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-09-11 | 2024-09-25 | 56 | Scope Variations
Prj.150 | Rift valley | Kenblast | Optimisation | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-11 | 2024-09-25 | 58 | Accessibility
Prj.151 | Rift valley | Kenblast | Optimisation | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-11 | 2024-09-25 | 58 | Accessibility
Prj.152 | Rift valley | Kenblast | Optimisation | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-11 | 2024-09-25 | 58 | Accessibility
Prj.153 | Rift valley | Kenblast | Optimisation | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-11 | 2024-09-25 | 58 | Materials Issuance
Prj.154 | Rift valley | Kenblast | Optimisation | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-11 | 2024-09-25 | 58 | Accessibility
Prj.155 | Coast | Kenblast | Optimisation | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-11 | 2024-09-25 | 58 | Accessibility
Prj.156 | Western | Kenblast | Optimisation | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-11 | 2024-09-25 | 58 | Materials Issuance
Prj.157 | Rift valley | Kenblast | Construction | 2024-04-18 | 2024-05-17 | 2023-10-31 | 2024-09-11 | 2024-09-25 | 330 | Scope Variations
Prj.158 | Rift valley | Kenblast | Survey | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-09-25 | 2024-08-30 | 30 | Quality Concerns
Prj.159 | Nairobi | Kenblast | Survey | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-09-25 | 2024-08-30 | 115 | Quality Concerns
Prj.160 | Nairobi | Kenblast | Survey | 2023-02-16 | 2023-02-16 | 2023-02-16 | 2024-09-11 | 2024-09-25 | 587 | Scope Variations
Prj.161 | Nairobi | Kenblast | Survey | 2024-07-24 | 2024-07-24 | 2024-07-24 | 2024-09-25 | 2024-08-30 | 37 | Quality Concerns
Prj.162 | Nairobi | Kenblast | Survey | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-09-25 | 2024-08-30 | 43 | Quality Concerns
Prj.163 | Nairobi | Kenblast | Survey | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-09-25 | 2024-08-30 | 46 | Quality Concerns
Prj.164 | Nairobi | Kenblast | Survey | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-09-25 | 2024-08-30 | 46 | Quality Concerns
Prj.165 | Nairobi | Kenblast | Survey | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-09-25 | 2024-08-30 | 46 | Quality Concerns
Prj.166 | Nairobi | Kenblast | Survey | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-09-25 | 2024-08-30 | 46 | Quality Concerns
Prj.167 | Nairobi | Kenblast | Survey | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-09-25 | 2024-08-30 | 79 | Quality Concerns
Prj.168 | Nairobi | Kenblast | Survey | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-09-25 | 2024-08-30 | 106 | Quality Concerns
Prj.169 | Mount kenya | Kenblast | Survey | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2024-09-11 | 2024-09-25 | 562 | Accessibility
Prj.170 | Western | Kenblast | Optimisation | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2024-09-11 | 2024-09-25 | 376 | Scope Variations
Prj.171 | Rift valley | Kenblast | Powering System | 2023-01-25 | 2023-01-25 | 2023-01-25 | 2024-09-11 | 2024-09-25 | 609 | Scope Variations
Prj.172 | Mount Kenya | Kenblast | Powering System | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2024-09-11 | 2024-09-25 | 818 | Scope Variations
Prj.173 | Mount Kenya | Kenblast | Powering System | 2022-03-16 | 2022-03-16 | 2022-03-16 | 2024-09-11 | 2024-09-25 | 924 | Scope Variations
Prj.174 | Coast | Kenblast | Survey | 2024-06-15 | 2024-06-15 | 2024-06-15 | 2024-09-25 | 2024-08-30 | 76 | Quality Concerns
Prj.175 | Nairobi | Kenblast | Survey | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-25 | 2024-08-30 | 18 | Quality Concerns
Prj.176 | Rift valley | Kenblast | Survey | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-09-11 | 2024-09-25 | 54 | Materials Issuance
Prj.177 | Nairobi | Kenblast | Survey | 2024-08-12 | 2024-07-02 | 2024-08-12 | 2024-09-11 | 2024-09-25 | 44 | Documentation
Prj.178 | Nairobi | Kenblast | Survey | 2024-06-15 | 2024-07-02 | 2024-06-15 | 2024-09-11 | 2024-09-25 | 102 | Accessibility
Prj.179 | Western | Kenblast | Survey | 2024-06-15 | 2024-07-02 | 2024-06-15 | 2024-09-11 | 2024-09-25 | 102 | Accessibility
Prj.180 | Nairobi | Kenblast | Survey | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-09-11 | 2024-09-25 | 56 | Quality Concerns
Prj.181 | Nairobi | Kenblast | Survey | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-09-11 | 2024-09-25 | 56 | Documentation
Prj.182 | Nairobi | Kenblast | Survey | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-09-11 | 2024-09-25 | 56 | Documentation
Prj.183 | Mount Kenya | Kenblast | Powering System | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-09-11 | 2024-09-25 | 32 | Scope Variations
Prj.184 | Nairobi | Starlenk | Powering System | 2024-07-31 | 2024-07-31 | 2024-08-02 | 2024-09-11 | 2024-09-25 | 54 | Client Manegment
Prj.185 | Kajiado | Starlenk | Construction | 2024-07-09 | 2024-07-09 | 2024-07-11 | 2024-09-11 | 2024-09-25 | 76 | Materials Issuance
Prj.186 | Nairobi | Kenblast | Survey | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-09-11 | 2024-09-25 | 56 | Documentation
Prj.187 | Nairobi | Kenblast | Optimisation | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-09-11 | 2024-09-25 | 56 | Materials Issuance
Prj.188 | Nairobi | Kenblast | Optimisation | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-09-11 | 2024-09-25 | 56 | Materials Issuance
Prj.1 | Rift valley | Kenblast | Construction | 2020-12-01 | 2020-12-05 | 2020-12-05 | 2024-03-30 | 2024-06-02 | 1275 | Quality Concerns
Prj.2 | Nairobi | Kenblast | Optimisation | 2022-03-22 | 2022-03-26 | 2022-03-26 | 2024-09-16 | 2024-09-30 | 919 | Materials Issuance
Prj.3 | Mount Kenya | Kenblast | Optimisation | 2023-02-22 | 2023-02-26 | 2023-02-26 | 2024-09-30 | 2024-08-25 | 546 | Quality Concerns
Prj.4 | Mount Kenya | Kenblast | Optimisation | 2023-03-19 | 2024-05-18 | 2023-03-23 | 2024-09-16 | 2024-09-30 | 557 | Accessibility
Prj.5 | Mount Kenya | Kenblast | Optimisation | 2023-03-19 | 2024-05-18 | 2023-03-23 | 2024-09-16 | 2024-09-30 | 557 | Accessibility
Prj.6 | Mount Kenya | Kenblast | Optimisation | 2023-03-19 | 2024-05-18 | 2023-03-23 | 2024-09-16 | 2024-09-30 | 557 | Accessibility
Prj.7 | Mount Kenya | Kenblast | Optimisation | 2023-03-19 | 2024-05-18 | 2023-03-23 | 2024-09-16 | 2024-09-30 | 557 | Accessibility
Prj.8 | Mount Kenya | Kenblast | Optimisation | 2023-03-19 | 2024-05-18 | 2023-03-23 | 2024-09-16 | 2024-09-30 | 557 | Accessibility
Prj.9 | Mount Kenya | Kenblast | Optimisation | 2023-03-19 | 2023-03-23 | 2023-03-23 | 2024-09-30 | 2024-07-22 | 487 | Quality Concerns
Prj.10 | Kiambu | Kenblast | Optimisation | 2023-04-04 | 2022-03-05 | 2023-08-20 | 2024-09-30 | 2024-06-19 | 304 | Quality Concerns
Prj.11 | Nairobi | Kenblast | Optimisation | 2023-07-06 | 2023-12-10 | 2023-08-07 | 2024-04-23 | 2024-04-23 | 260 | Quality Concerns
Prj.12 | Mount Kenya | Kenblast | Construction | 2023-08-29 | 2023-09-02 | 2023-10-01 | 2024-02-05 | 2024-09-30 | 365 | Materials Issuance
Prj.13 | Rift valley | Kenblast | Construction | 2023-09-02 | 2023-10-22 | 2023-11-05 | 2024-09-16 | 2024-09-30 | 330 | Scope Variations
Prj.14 | Western | Kenblast | Optimisation | 2023-09-07 | 2024-04-23 | 2024-01-08 | 2024-09-30 | 2024-05-11 | 124 | Quality Concerns
Prj.15 | Nairobi | Kenblast | Optimisation | 2023-09-16 | 2023-09-20 | 2024-02-08 | 2024-09-30 | 2024-05-04 | 86 | Quality Concerns
Prj.16 | Nairobi | Kenblast | Optimisation | 2023-09-16 | 2023-09-20 | 2024-01-11 | 2024-09-30 | 2024-02-25 | 45 | Quality Concerns
Prj.17 | Ksumu | Starlenk | Optimisation | 2023-09-21 | 2023-09-25 | 2023-10-09 | 2024-09-16 | 2024-09-30 | 357 | Quality Concerns
Prj.18 | Nairobi | Kenblast | Optimisation | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-09-30 | 2024-06-05 | 98 | Quality Concerns
Prj.19 | Nairobi | Kenblast | Optimisation | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-09-30 | 2024-06-05 | 98 | Quality Concerns
Prj.20 | Nairobi | Kenblast | Optimisation | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-09-30 | 2024-06-05 | 98 | Quality Concerns
Prj.21 | Nairobi | Kenblast | Optimisation | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-09-30 | 2024-06-05 | 98 | Quality Concerns
Prj.22 | Nairobi | Kenblast | Optimisation | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-09-30 | 2024-06-05 | 98 | Quality Concerns
Prj.23 | Nairobi | Kenblast | Optimisation | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-09-30 | 2024-06-05 | 98 | Quality Concerns
Prj.24 | Nairobi | Kenblast | Survey | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-09-16 | 2024-09-30 | 215 | Scope Variations
Prj.25 | Mount kenya | Starlenk | Construction | 2023-04-01 | 2023-04-05 | 2023-04-05 | 2024-09-30 | 2024-09-17 | 531 | Quality Concerns
Prj.26 | Likoni | Starlenk | Construction | 2023-09-25 | 2023-09-29 | 2023-10-01 | 2024-09-16 | 2024-09-30 | 365 | Documentation
Prj.27 | Nairobi | Kenblast | Optimisation | 2023-09-29 | 2023-12-17 | 2023-12-20 | 2024-09-30 | 2024-03-19 | 90 | Quality Concerns
Prj.28 | Kajiado | Starlenk | Construction | 2023-10-18 | 2023-10-22 | 2023-10-26 | 2024-09-30 | 2024-09-24 | 334 | Quality Concerns
Prj.29 | Kilifi | Starlenk | Construction | 2023-10-19 | 2023-10-23 | 2023-10-25 | 2024-09-30 | 2024-08-27 | 307 | Quality Concerns
Prj.30 | Elgeiyo marakwet | Starlenk | Construction | 2023-11-01 | 2023-11-05 | 2023-11-07 | 2024-09-30 | 2024-09-16 | 314 | Quality Concerns
Prj.31 | Nairobi | Kenblast | Construction | 2023-11-05 | 2023-12-11 | 2024-01-17 | 2024-09-30 | 2024-09-11 | 238 | Quality Concerns
Prj.32 | Kiambu | Starlenk | Construction | 2023-11-21 | 2023-11-25 | 2023-11-27 | 2024-09-16 | 2024-09-30 | 308 | Documentation
Prj.33 | Machakos | Starlenk | Construction | 2023-11-23 | 2023-11-27 | 2023-11-29 | 2024-09-16 | 2024-09-30 | 306 | Quality Concerns
Prj.34 | Nairobi | Kenblast | Survey | 2023-11-29 | 2024-02-27 | 2024-02-28 | 2024-09-16 | 2024-09-30 | 215 | Accessibility
Prj.35 | Mount kenya | Starlenk | Construction | 2023-11-05 | 2023-11-09 | 2023-11-09 | 2024-09-16 | 2024-09-30 | 326 | Quality Concerns
Prj.36 | Rift valley | Kenblast | Optimisation | 2023-12-06 | 2024-01-20 | 2023-12-14 | 2024-09-16 | 2024-09-30 | 291 | Quality Concerns
Prj.37 | Coast | Starlenk | Powering System | 2023-12-06 | 2023-12-10 | 2024-03-03 | 2024-09-16 | 2024-09-30 | 211 | Quality Concerns
Prj.38 | Coast | Starlenk | Powering System | 2023-12-06 | 2023-12-11 | 2024-03-03 | 2024-09-16 | 2024-09-30 | 211 | Quality Concerns
Prj.39 | Nairobi North | Kenblast | Powering System | 2023-12-09 | 2023-12-13 | 2023-12-21 | 2024-09-16 | 2024-09-30 | 284 | Accessibility
Prj.40 | Elgeiyo marakwet | Starlenk | Construction | 2023-12-11 | 2023-12-15 | 2023-12-17 | 2024-01-30 | 2024-09-30 | 288 | Quality Concerns
Prj.41 | Nairobi | Kenblast | Optimisation | 2023-12-12 | 2023-12-15 | 2023-12-18 | 2024-05-27 | 2024-05-27 | 161 | Quality Concerns
Prj.42 | Nairobi | Starlenk | Construction | 2023-12-21 | 2023-12-25 | 2023-12-27 | 2024-05-06 | 2024-09-30 | 278 | Documentation
Prj.43 | Nairobi | Kenblast | Construction | 2023-12-29 | 2024-01-20 | 2024-01-26 | 2024-03-17 | 2024-03-17 | 51 | Quality Concerns
Prj.44 | Mount kenya | Starlenk | Construction | 2023-12-05 | 2023-12-11 | 2023-12-11 | 2024-09-30 | 2024-08-10 | 243 | Quality Concerns
Prj.45 | Samburu | Starlenk | Construction | 2024-01-04 | 2024-01-08 | 2024-01-10 | 2024-09-16 | 2024-09-30 | 264 | Client Manegment
Prj.46 | Rift valley | Kenblast | Optimisation | 2024-01-13 | 2024-01-17 | 2024-02-11 | 2024-09-16 | 2024-09-30 | 232 | Quality Concerns
Prj.47 | Rift valley | Kenblast | Optimisation | 2024-01-16 | 2024-03-02 | 2024-03-19 | 2024-05-25 | 2024-05-25 | 67 | Quality Concerns
Prj.48 | Mount Kenya | Kenblast | Construction | 2024-01-16 | 2024-01-20 | 2024-02-15 | 2024-06-16 | 2024-07-22 | 158 | Quality Concerns
Prj.49 | Western | Kenblast | Optimisation | 2024-01-24 | 2024-01-28 | 2024-02-26 | 2024-05-20 | 2024-05-20 | 84 | Quality Concerns
Prj.50 | Western | Kenblast | Optimisation | 2024-01-25 | 2024-02-02 | 2024-02-01 | 2024-09-30 | 2024-07-13 | 163 | Quality Concerns
Prj.51 | Rift valley | Kenblast | Optimisation | 2024-02-06 | 2024-02-10 | 2024-03-04 | 2024-09-30 | 2024-06-04 | 92 | Quality Concerns
Prj.52 | Rift valley | Kenblast | Optimisation | 2024-02-06 | 2024-02-10 | 2024-03-05 | 2024-09-30 | 2024-06-04 | 91 | Quality Concerns
Prj.53 | Nairobi | Starlenk | Construction | 2024-02-11 | 2024-02-15 | 2024-02-17 | 2024-09-30 | 2024-07-13 | 147 | Quality Concerns
Prj.54 | Nairobi | Kenblast | Construction | 2024-02-13 | 2024-02-21 | 2024-04-08 | 2024-09-30 | 2024-08-28 | 142 | Quality Concerns
Prj.55 | Makueni | Starlenk | Construction | 2024-02-14 | 2024-02-18 | 2024-02-20 | 2024-09-16 | 2024-09-30 | 223 | Quality Concerns
Prj.56 | Western | Kenblast | Optimisation | 2024-02-17 | 2024-02-21 | 2024-02-25 | 2024-09-30 | 2024-05-01 | 66 | Quality Concerns
Prj.57 | Western | Kenblast | Optimisation | 2024-02-17 | 2024-02-21 | 2024-02-26 | 2024-09-30 | 2024-08-25 | 181 | Quality Concerns
Prj.58 | Nairobi | Kenblast | Optimisation | 2024-02-24 | 2024-02-28 | 2024-06-17 | 2024-09-30 | 2024-09-23 | 98 | Quality Concerns
Prj.59 | Nairobi | Kenblast | Optimisation | 2024-02-28 | 2024-03-03 | 2024-03-04 | 2024-09-30 | 2024-05-28 | 85 | Quality Concerns
Prj.60 | mount kenya | Kenblast | Optimisation | 2024-03-03 | 2024-03-07 | 2024-06-09 | 2024-09-30 | 2024-08-25 | 77 | Quality Concerns
Prj.61 | Mount Kenya | Kenblast | Optimisation | 2024-03-03 | 2024-03-07 | 2024-06-02 | 2024-09-30 | 2024-06-27 | 25 | Quality Concerns
Prj.62 | Rift valley | Kenblast | Optimisation | 2024-03-09 | 2024-03-13 | 2024-03-19 | 2024-09-30 | 2024-05-28 | 70 | Quality Concerns
Prj.63 | Homa bay | Starlenk | Construction | 2024-03-13 | 2024-03-17 | 2024-03-19 | 2024-09-16 | 2024-09-30 | 195 | Client Manegment
Prj.64 | Nairobi | Kenblast | Optimisation | 2024-03-22 | 2024-03-26 | 2024-03-28 | 2024-09-30 | 2024-06-03 | 67 | Quality Concerns
Prj.65 | Nairobi | Starlenk | Powering System | 2024-03-24 | 2024-03-28 | 2024-03-28 | 2024-09-30 | 2024-09-22 | 178 | Quality Concerns
Prj.66 | Embu | Starlenk | Construction | 2024-03-28 | 2024-04-01 | 2024-04-03 | 2024-09-30 | 2024-09-17 | 167 | Quality Concerns
Prj.67 | Kiambu | Starlenk | Construction | 2024-03-30 | 2024-04-12 | 2024-04-14 | 2024-09-16 | 2024-09-30 | 169 | Client Manegment
Prj.68 | Migori | Starlenk | Construction | 2024-03-30 | 2024-04-10 | 2024-04-12 | 2024-09-16 | 2024-09-30 | 171 | Client Manegment
Prj.69 | Kwale | Starlenk | Construction | 2024-03-30 | 2024-04-10 | 2024-04-12 | 2024-09-16 | 2024-09-30 | 171 | Client Manegment
Prj.70 | Rift valley | Kenblast | Powering System | 2024-03-29 | 2024-06-11 | 2024-06-12 | 2024-09-30 | 2024-09-21 | 101 | Quality Concerns
Prj.71 | Rift valley | Kenblast | Optimisation | 2024-04-04 | 2024-05-21 | 2024-05-21 | 2024-09-30 | 2024-07-17 | 57 | Quality Concerns
Prj.72 | Mount Kenya | Kenblast | Optimisation | 2024-04-04 | 2024-05-16 | 2024-05-16 | 2024-09-30 | 2024-06-18 | 33 | Quality Concerns
Prj.73 | Mount Kenya | Kenblast | Optimisation | 2024-04-04 | 2024-04-08 | 2024-04-08 | 2024-09-16 | 2024-09-30 | 175 | Accessibility
Prj.74 | Mount Kenya | Kenblast | Optimisation | 2024-04-04 | 2024-04-08 | 2024-04-08 | 2024-09-16 | 2024-09-30 | 175 | Accessibility
Prj.75 | Mount Kenya | Kenblast | Optimisation | 2024-04-04 | 2024-04-08 | 2024-04-08 | 2024-09-16 | 2024-09-30 | 175 | Accessibility
Prj.76 | Rift valley | Kenblast | Optimisation | 2024-04-04 | 2024-04-08 | 2024-04-08 | 2024-09-30 | 2024-08-14 | 128 | Quality Concerns
Prj.77 | Mount Kenya | Kenblast | Optimisation | 2024-04-04 | 2024-04-08 | 2024-04-08 | 2024-09-16 | 2024-09-30 | 175 | Accessibility
Prj.78 | Mount Kenya | Kenblast | Optimisation | 2024-04-04 | 2024-04-08 | 2024-04-08 | 2024-09-30 | 2024-08-10 | 124 | Quality Concerns
Prj.79 | Nairobi | Kenblast | Powering System | 2024-04-04 | 2024-06-27 | 2024-06-28 | 2024-09-30 | 2024-09-18 | 82 | Quality Concerns
Prj.80 | Nairobi | Kenblast | Optimisation | 2024-04-06 | 2024-04-10 | 2024-04-14 | 2024-09-16 | 2024-09-30 | 169 | Accessibility
Prj.81 | Mount Kenya | Kenblast | Optimisation | 2024-04-10 | 2024-04-14 | 2024-06-11 | 2024-09-30 | 2024-06-24 | 13 | Quality Concerns
Prj.82 | Mount Kenya | Kenblast | Optimisation | 2024-04-10 | 2024-04-14 | 2024-06-04 | 2024-09-30 | 2024-06-24 | 20 | Quality Concerns
Prj.83 | Mount Kenya | Kenblast | Optimisation | 2024-04-10 | 2024-04-14 | 2024-04-14 | 2024-09-16 | 2024-09-30 | 169 | Accessibility
Prj.84 | Mount Kenya | Kenblast | Optimisation | 2024-04-10 | 2024-04-14 | 2024-07-04 | 2024-09-30 | 2024-08-10 | 37 | Quality Concerns
Prj.85 | Mount Kenya | Kenblast | Optimisation | 2024-04-13 | 2024-04-17 | 2024-07-15 | 2024-09-16 | 2024-09-30 | 77 | Scope Variations
Prj.86 | Nairobi East | Kenblast | Optimisation | 2024-04-17 | 2024-05-19 | 2024-05-22 | 2024-09-30 | 2024-06-18 | 27 | Quality Concerns
Prj.87 | Mount Kenya | Kenblast | Optimisation | 2024-04-17 | 2024-04-21 | 2024-04-21 | 2024-09-16 | 2024-09-30 | 162 | Accessibility
Prj.88 | Mount Kenya | Kenblast | Optimisation | 2024-04-17 | 2024-04-21 | 2024-07-18 | 2024-09-30 | 2024-09-11 | 55 | Quality Concerns
Prj.89 | Nairobi East | Kenblast | Optimisation | 2024-04-23 | 2024-05-21 | 2024-05-22 | 2024-09-30 | 2024-06-18 | 27 | Quality Concerns
Prj.90 | Mount Kenya | Kenblast | Optimisation | 2024-04-23 | 2024-04-27 | 2024-06-21 | 2024-09-30 | 2024-07-13 | 22 | Quality Concerns
Prj.91 | Mount Kenya | Kenblast | Optimisation | 2024-04-23 | 2024-04-27 | 2024-04-27 | 2024-09-16 | 2024-09-30 | 156 | Accessibility
Prj.92 | Mount Kenya | Kenblast | Optimisation | 2024-04-26 | 2024-04-30 | 2024-05-21 | 2024-09-30 | 2024-08-25 | 96 | Quality Concerns
Prj.93 | Rift valley | Kenblast | Powering System | 2024-04-29 | 2024-05-03 | 2024-05-03 | 2024-09-16 | 2024-09-30 | 150 | Materials Issuance
Prj.94 | Nairobi | Kenblast | Optimisation | 2024-05-02 | 2024-05-08 | 2024-05-15 | 2024-09-30 | 2024-06-26 | 42 | Quality Concerns
Prj.95 | Kericho | Starlenk | Construction | 2024-05-02 | 2024-05-03 | 2024-05-09 | 2024-09-16 | 2024-09-30 | 144 | Quality Concerns
Prj.96 | Busia | Starlenk | Construction | 2024-05-02 | 2024-05-03 | 2024-05-09 | 2024-09-16 | 2024-09-30 | 144 | Client Manegment
Prj.97 | Vihiga | Starlenk | Construction | 2024-05-02 | 2024-05-03 | 2024-05-09 | 2024-09-16 | 2024-09-30 | 144 | Quality Concerns
Prj.98 | Nairobi East | Starlenk | Optimisation | 2024-05-04 | 2024-05-07 | 2024-05-13 | 2024-06-09 | 2024-06-18 | 36 | Quality Concerns
Prj.99 | Nairobi East | Starlenk | Optimisation | 2024-05-04 | 2024-05-08 | 2024-05-13 | 2024-06-09 | 2024-06-18 | 36 | Quality Concerns
Prj.100 | Rift valley | Kenblast | Optimisation | 2024-05-13 | 2024-05-17 | 2024-05-26 | 2024-09-30 | 2024-08-25 | 91 | Quality Concerns
Prj.101 | Rift valley | Kenblast | Optimisation | 2024-05-16 | 2024-05-20 | 2024-05-28 | 2024-09-30 | 2024-07-23 | 56 | Quality Concerns
Prj.102 | Nairobi | Kenblast | Optimisation | 2024-05-16 | 2024-05-20 | 2024-05-29 | 2024-09-30 | 2024-08-05 | 68 | Quality Concerns
Prj.103 | Rift valley | Kenblast | Powering System | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-09-16 | 2024-09-30 | 215 | Scope Variations
Prj.104 | Rift valley | Kenblast | Powering System | 2023-09-04 | 2023-09-08 | 2023-09-08 | 2024-09-16 | 2024-09-30 | 388 | Scope Variations
Prj.105 | Mt. Kenya | Kenblast | Powering System | 2024-02-16 | 2024-02-20 | 2024-02-20 | 2024-09-16 | 2024-09-30 | 223 | Scope Variations
Prj.106 | Nairobi | Kenblast | Optimisation | 2023-06-27 | 2023-07-01 | 2023-07-01 | 2024-09-30 | 2024-06-04 | 339 | Quality Concerns
Prj.107 | Western | Kenblast | Optimisation | 2024-04-03 | 2024-04-07 | 2024-04-07 | 2024-09-16 | 2024-09-30 | 176 | Materials Issuance
Prj.108 | Rift valley | Kenblast | Powering System | 2020-10-28 | 2020-11-01 | 2020-11-01 | 2024-09-16 | 2024-09-30 | 1429 | Scope Variations
Prj.109 | Western | Kenblast | Optimisation | 2024-05-10 | 2024-05-14 | 2024-07-13 | 2024-09-16 | 2024-09-30 | 79 | Documentation
Prj.110 | Mt. Kenya | Kenblast | Powering System | 2024-05-06 | 2024-05-10 | 2024-05-10 | 2024-09-16 | 2024-09-30 | 143 | Materials Issuance
Prj.111 | Nairobi | Kenblast | Powering System | 2024-05-06 | 2024-05-10 | 2024-05-10 | 2024-09-16 | 2024-09-30 | 143 | Materials Issuance
Prj.112 | Mount kenya | Starlenk | Construction | 2024-05-29 | 2024-06-02 | 2024-06-03 | 2024-09-16 | 2024-09-30 | 119 | Client Manegment
Prj.113 | Rift valley | Starlenk | Construction | 2024-05-29 | 2024-06-02 | 2024-06-03 | 2024-09-16 | 2024-09-30 | 119 | Quality Concerns
Prj.114 | Coast | Starlenk | Construction | 2024-05-29 | 2024-06-02 | 2024-06-03 | 2024-09-16 | 2024-09-30 | 119 | Quality Concerns
Prj.115 | Nairobi | Kenblast | Optimisation | 2024-06-04 | 2024-06-08 | 2024-07-10 | 2024-09-30 | 2024-07-17 | 7 | Quality Concerns
Prj.116 | Western | Kenblast | Optimisation | 2024-06-04 | 2024-06-08 | 2024-07-13 | 2024-09-16 | 2024-09-30 | 79 | Quality Concerns
Prj.117 | Mount Kenya | Kenblast | Optimisation | 2024-06-04 | 2024-06-08 | 2024-07-03 | 2024-09-16 | 2024-09-30 | 89 | Quality Concerns
Prj.118 | Western | Kenblast | Optimisation | 2024-06-04 | 2024-06-08 | 2024-07-13 | 2024-09-16 | 2024-09-30 | 79 | Accessibility
Prj.119 | Rift valley | Kenblast | Powering System | 2024-06-05 | 2024-06-09 | 2024-06-09 | 2024-09-16 | 2024-09-30 | 113 | Materials Issuance
Prj.120 | Nairobi East | Kenblast | Powering System | 2024-06-05 | 2024-06-09 | 2024-06-09 | 2024-09-16 | 2024-09-30 | 113 | Materials Issuance
Prj.121 | Nairobi East | Kenblast | Powering System | 2024-06-05 | 2024-06-09 | 2024-06-09 | 2024-09-16 | 2024-09-30 | 113 | Materials Issuance
Prj.122 | Nairobi West | Kenblast | Construction | 2024-06-05 | 2024-06-09 | 2024-06-11 | 2024-09-16 | 2024-09-30 | 111 | Scope Variations
Prj.123 | Western | Kenblast | Optimisation | 2024-06-07 | 2024-07-11 | 2024-07-18 | 2024-09-16 | 2024-09-30 | 74 | Scope Variations
Prj.124 | Mount Kenya | Starlenk | Construction | 2024-06-11 | 2024-06-15 | 2024-06-16 | 2024-09-16 | 2024-09-30 | 106 | Client Manegment
Prj.125 | Western | Kenblast | Optimisation | 2024-06-14 | 2024-06-18 | 2024-06-18 | 2024-09-16 | 2024-09-30 | 104 | Accessibility
Prj.126 | Western | Kenblast | Optimisation | 2024-06-14 | 2024-06-18 | 2024-06-18 | 2024-09-16 | 2024-09-30 | 104 | Accessibility
Prj.127 | Rift valley | Starlenk | Optimisation | 2024-06-14 | 2024-06-18 | 2024-06-27 | 2024-09-16 | 2024-09-30 | 95 | Client Manegment
Prj.128 | Mount Kenya | Starlenk | Construction | 2024-06-16 | 2024-06-20 | 2024-06-22 | 2024-09-16 | 2024-09-30 | 100 | Scope Variations
Prj.129 | Nairobi | Starlenk | Construction | 2024-06-16 | 2024-06-20 | 2024-06-21 | 2024-09-16 | 2024-09-30 | 101 | Client Manegment
Prj.130 | Nairobi | Starlenk | Construction | 2024-07-03 | 2024-07-07 | 2024-07-09 | 2024-09-16 | 2024-09-30 | 83 | Client Manegment
Prj.131 | Nairobi | Starlenk | Construction | 2024-07-03 | 2024-07-07 | 2024-07-09 | 2024-09-16 | 2024-09-30 | 83 | Client Manegment
Prj.132 | Nairobi | Starlenk | Construction | 2024-07-03 | 2024-07-07 | 2024-07-09 | 2024-09-16 | 2024-09-30 | 83 | Quality Concerns
Prj.133 | kitui | Kenblast | Powering System | 2024-06-29 | 2024-07-07 | 2024-07-09 | 2024-09-16 | 2024-09-30 | 83 | Accessibility
Prj.134 | Wajir | Kenblast | Powering System | 2024-06-29 | 2024-07-07 | 2024-07-09 | 2024-09-16 | 2024-09-30 | 83 | Accessibility
Prj.135 | Nairobi | Kenblast | Survey | 2024-07-03 | 2024-07-07 | 2024-07-09 | 2024-09-16 | 2024-09-30 | 83 | Quality Concerns
Prj.136 | Western | Kenblast | Survey | 2024-07-03 | 2024-07-07 | 2024-07-09 | 2024-09-16 | 2024-09-30 | 83 | Materials Issuance
Prj.137 | Western | Kenblast | Optimisation | 2024-07-09 | 2024-07-13 | 2024-08-02 | 2024-09-16 | 2024-09-30 | 59 | Scope Variations
Prj.138 | Nairobi | Starlenk | Construction | 2024-07-10 | 2024-07-14 | 2024-07-16 | 2024-09-16 | 2024-09-30 | 76 | Materials Issuance
Prj.139 | Nairobi | Starlenk | Powering System | 2024-07-11 | 2024-07-15 | 2024-08-03 | 2024-09-16 | 2024-09-30 | 58 | Materials Issuance
Prj.140 | Kisumu | Starlenk | Powering System | 2024-07-11 | 2024-07-15 | 2024-07-15 | 2024-09-16 | 2024-09-30 | 77 | Materials Issuance
Prj.141 | Kisumu | Starlenk | Powering System | 2024-07-11 | 2024-07-15 | 2024-07-15 | 2024-09-16 | 2024-09-30 | 77 | Materials Issuance
Prj.142 | Kiambu | Starlenk | Powering System | 2024-07-11 | 2024-07-15 | 2024-07-15 | 2024-09-16 | 2024-09-30 | 77 | Materials Issuance
Prj.143 | Muranga | Starlenk | Powering System | 2024-07-11 | 2024-07-15 | 2024-08-03 | 2024-09-16 | 2024-09-30 | 58 | Materials Issuance
Prj.144 | Nairobi | Kenblast | Survey | 2024-07-24 | 2024-07-28 | 2024-08-10 | 2024-09-16 | 2024-09-30 | 51 | Scope Variations
Prj.145 | Muranga | Starlenk | Construction | 2024-08-11 | 2024-08-04 | 2024-08-17 | 2024-09-16 | 2024-09-30 | 44 | Materials Issuance
Prj.146 | Tangulbei | Starlenk | Construction | 2024-07-31 | 2024-08-04 | 2024-08-04 | 2024-09-16 | 2024-09-30 | 57 | Client Manegment
Prj.147 | Nairobi | Starlenk | Construction | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-09-16 | 2024-09-30 | 56 | Client Manegment
Prj.148 | Nairobi | Kenblast | Optimisation | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-09-16 | 2024-09-30 | 56 | Scope Variations
Prj.149 | Nairobi | Kenblast | Optimisation | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-09-16 | 2024-09-30 | 56 | Scope Variations
Prj.150 | Rift valley | Kenblast | Optimisation | 2024-07-30 | 2024-08-03 | 2024-08-03 | 2024-09-16 | 2024-09-30 | 58 | Accessibility
Prj.151 | Rift valley | Kenblast | Optimisation | 2024-07-30 | 2024-08-03 | 2024-08-03 | 2024-09-16 | 2024-09-30 | 58 | Accessibility
Prj.152 | Rift valley | Kenblast | Optimisation | 2024-07-30 | 2024-08-03 | 2024-08-03 | 2024-09-16 | 2024-09-30 | 58 | Accessibility
Prj.153 | Rift valley | Kenblast | Optimisation | 2024-07-30 | 2024-08-03 | 2024-08-03 | 2024-09-16 | 2024-09-30 | 58 | Materials Issuance
Prj.154 | Rift valley | Kenblast | Optimisation | 2024-07-30 | 2024-08-03 | 2024-08-03 | 2024-09-16 | 2024-09-30 | 58 | Accessibility
Prj.155 | Coast | Kenblast | Optimisation | 2024-07-30 | 2024-08-03 | 2024-08-03 | 2024-09-16 | 2024-09-30 | 58 | Accessibility
Prj.156 | Western | Kenblast | Optimisation | 2024-07-30 | 2024-08-03 | 2024-08-03 | 2024-09-16 | 2024-09-30 | 58 | Materials Issuance
Prj.157 | Rift valley | Kenblast | Construction | 2024-04-19 | 2024-05-22 | 2023-11-05 | 2024-09-16 | 2024-09-30 | 330 | Scope Variations
Prj.158 | Rift valley | Kenblast | Survey | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-09-30 | 2024-09-04 | 30 | Quality Concerns
Prj.159 | Nairobi | Kenblast | Survey | 2024-05-08 | 2024-05-12 | 2024-05-12 | 2024-09-30 | 2024-09-04 | 115 | Quality Concerns
Prj.160 | Nairobi | Kenblast | Survey | 2023-02-17 | 2023-02-21 | 2023-02-21 | 2024-09-16 | 2024-09-30 | 587 | Scope Variations
Prj.161 | Nairobi | Kenblast | Survey | 2024-07-25 | 2024-07-29 | 2024-07-29 | 2024-09-30 | 2024-09-04 | 37 | Quality Concerns
Prj.162 | Nairobi | Kenblast | Survey | 2024-07-19 | 2024-07-23 | 2024-07-23 | 2024-09-30 | 2024-09-04 | 43 | Quality Concerns
Prj.163 | Nairobi | Kenblast | Survey | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-09-30 | 2024-09-04 | 46 | Quality Concerns
Prj.164 | Nairobi | Kenblast | Survey | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-09-30 | 2024-09-04 | 46 | Quality Concerns
Prj.165 | Nairobi | Kenblast | Survey | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-09-30 | 2024-09-04 | 46 | Quality Concerns
Prj.166 | Nairobi | Kenblast | Survey | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-09-30 | 2024-09-04 | 46 | Quality Concerns
Prj.167 | Nairobi | Kenblast | Survey | 2024-06-13 | 2024-06-17 | 2024-06-17 | 2024-09-30 | 2024-09-04 | 79 | Quality Concerns
Prj.168 | Nairobi | Kenblast | Survey | 2024-05-17 | 2024-05-21 | 2024-05-21 | 2024-09-30 | 2024-09-04 | 106 | Quality Concerns
Prj.169 | Mount kenya | Kenblast | Survey | 2023-03-14 | 2023-03-18 | 2023-03-18 | 2024-09-16 | 2024-09-30 | 562 | Accessibility
Prj.170 | Western | Kenblast | Optimisation | 2023-09-16 | 2023-09-20 | 2023-09-20 | 2024-09-16 | 2024-09-30 | 376 | Scope Variations
Prj.171 | Rift valley | Kenblast | Powering System | 2023-01-26 | 2023-01-30 | 2023-01-30 | 2024-09-16 | 2024-09-30 | 609 | Scope Variations
Prj.172 | Mount Kenya | Kenblast | Powering System | 2022-07-01 | 2022-07-05 | 2022-07-05 | 2024-09-16 | 2024-09-30 | 818 | Scope Variations
Prj.173 | Mount Kenya | Kenblast | Powering System | 2022-03-17 | 2022-03-21 | 2022-03-21 | 2024-09-16 | 2024-09-30 | 924 | Scope Variations
Prj.174 | Coast | Kenblast | Survey | 2024-06-16 | 2024-06-20 | 2024-06-20 | 2024-09-30 | 2024-09-04 | 76 | Quality Concerns
Prj.175 | Nairobi | Kenblast | Survey | 2024-08-13 | 2024-08-17 | 2024-08-17 | 2024-09-30 | 2024-09-04 | 18 | Quality Concerns
Prj.176 | Rift valley | Kenblast | Survey | 2024-08-03 | 2024-08-07 | 2024-08-07 | 2024-09-16 | 2024-09-30 | 54 | Materials Issuance
Prj.177 | Nairobi | Kenblast | Survey | 2024-08-13 | 2024-07-07 | 2024-08-17 | 2024-09-16 | 2024-09-30 | 44 | Documentation
Prj.178 | Nairobi | Kenblast | Survey | 2024-06-16 | 2024-07-07 | 2024-06-20 | 2024-09-16 | 2024-09-30 | 102 | Accessibility
Prj.179 | Western | Kenblast | Survey | 2024-06-16 | 2024-07-07 | 2024-06-20 | 2024-09-16 | 2024-09-30 | 102 | Accessibility
Prj.180 | Nairobi | Kenblast | Survey | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-09-16 | 2024-09-30 | 56 | Quality Concerns
Prj.181 | Nairobi | Kenblast | Survey | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-09-16 | 2024-09-30 | 56 | Documentation
Prj.182 | Nairobi | Kenblast | Survey | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-09-16 | 2024-09-30 | 56 | Documentation
Prj.183 | Mount Kenya | Kenblast | Powering System | 2024-08-25 | 2024-08-29 | 2024-08-29 | 2024-09-16 | 2024-09-30 | 32 | Scope Variations
Prj.184 | Nairobi | Starlenk | Powering System | 2024-08-01 | 2024-08-05 | 2024-08-07 | 2024-09-16 | 2024-09-30 | 54 | Client Manegment
Prj.185 | Kajiado | Starlenk | Construction | 2024-07-10 | 2024-07-14 | 2024-07-16 | 2024-09-16 | 2024-09-30 | 76 | Materials Issuance
Prj.186 | Nairobi | Kenblast | Survey | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-09-16 | 2024-09-30 | 56 | Documentation
Prj.187 | Nairobi | Kenblast | Optimisation | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-09-16 | 2024-09-30 | 56 | Materials Issuance
Prj.188 | Nairobi | Kenblast | Optimisation | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-09-16 | 2024-09-30 | 56 | Materials Issuance